## RSChatBacklog
Projects | Start date | End date | Sprint | Priority | Type | Status | Started | Finished | Inactivity (h) | Notes | Duration | Inactivity time | Active time | Created | Epic | Engineers | Product Manager | Timeline | Tasks | URL
Create ER diagram | 2022-06-11 | 2022-06-11 | Sprint 01 | High | Documentation 📘, Initialization 🎉 | Complete | June 11, 2022 13:15 | June 11, 2022 22:15 | 3 |  | 32400 | 10800 | 21600 | June 11, 2022 2:14 AM
Create Relational diagram | 2022-06-11 | 2022-06-12 | Sprint 01 | High | Documentation 📘, Initialization 🎉 | Complete | June 11, 2022 22:18 | June 12, 2022 2:30 | 3 |  | 15120 | 10800 | 4320 | June 11, 2022 3:24 PM
Translate Relational diagram to SQL | 2022-06-12 | 2022-06-13 | Sprint 01 | High | Initialization 🎉 | Complete | June 12, 2022 23:40 | June 13, 2022 0:20 | 0 |  | 2400 | 0 | 2400 | June 12, 2022 2:31 AM
Create the model classes with Cayenne Modeler | 2022-06-13 | 2022-06-13 | Sprint 01 | Medium | Initialization 🎉 | Cancelled | June 13, 2022 0:20 | June 13, 2022 0:45 | 0 | Migration to JPA | 1500 | 0 | 1500 | June 11, 2022 2:15 AM
From Cayenne to JPA | 2022-06-13 | 2022-06-13 | Sprint 01 | High | Configuration ⚙️, Task 🔨 | Complete | June 13, 2022 13:53 | June 13, 2022 18:00 | 3 |  | 14820 | 10800 | 4020 | June 13, 2022 1:53 PM
Backend login with JWT tokens | 2022-06-13 | 2022-06-14 | Sprint 01 | High | Task 🔨 | Complete | June 13, 2022 19:00 | June 14, 2022 2:30 | 2 |  | 27000 | 7200 | 19800 | June 13, 2022 10:02 PM
Configure Spring security with basic requests | 2022-06-13 | 2022-06-15 | Sprint 01 | Critical 🔥 | Configuration ⚙️, Task 🔨 | Complete | June 13, 2022 23:15 | June 15, 2022 1:55 | 9 |  | 96000 | 32400 | 63600 | June 13, 2022 1:34 PM
Backend routes with constants | 2022-06-14 | 2022-06-14 | Sprint 01 | Medium | Configuration ⚙️, Task 🔨 | Complete | June 14, 2022 13:16 | June 14, 2022 14:12 | 0 |  | 3360 | 0 | 3360 | June 14, 2022 8:43 PM
Be able to manage request in controller after passing a Filter | 2022-06-14 | 2022-06-14 | Sprint 01 | Critical 🔥 | Configuration ⚙️ | Complete | June 14, 2022 17:30 | June 14, 2022 20:40 | 1 |  | 11400 | 3600 | 7800 | June 14, 2022 8:39 PM
Implement SessionService with capability to save, delete | 2022-06-14 | 2022-06-14 | Sprint 01 | High | Task 🔨 | Complete | June 14, 2022 21:37 | June 14, 2022 22:00 | 0 |  | 1380 | 0 | 1380 | June 14, 2022 9:36 PM
Update DB to include refreshToken | 2022-06-14 | 2022-06-14 | Sprint 01 | High | Configuration ⚙️, Task 🔨 | Complete | June 14, 2022 21:43 | June 14, 2022 21:48 | 0 |  | 300 | 0 | 300 | June 14, 2022 9:43 PM
Improve Filters with annotations | 2022-06-15 | 2022-06-15 | Sprint 01 | Medium | Refactor 🛠️ | Cancelled | June 15, 2022 0:18 | June 15, 2022 0:27 | 0 |  | 540 | 0 | 540 | June 14, 2022 9:34 PM
Solve problem with user creation by admins | 2022-06-15 | 2022-06-15 | Sprint 01 | Critical 🔥 | Bug 🐞, Task 🔨 | Complete | June 15, 2022 0:29 | June 15, 2022 1:08 | 0 | I’m a bit idiot | 2340 | 0 | 2340 | June 15, 2022 12:29 AM
Fix login controller does not work after AuthenticationFilter | 2022-06-15 | 2022-06-15 | Sprint 01 | Critical 🔥 | Bug 🐞, Configuration ⚙️ | Complete | June 15, 2022 13:00 | June 15, 2022 14:10 | 0 | Problem with the LogoutFilter. Removed | 4200 | 0 | 4200 | June 15, 2022 2:58 AM
Fix CORS security | 2022-06-15 | 2022-06-15 | Sprint 01 | Critical 🔥 | Bug 🐞, Task 🔨 | Complete | June 15, 2022 17:50 | June 15, 2022 18:56 | 0 | Improved using WebMvcConfigurer in main class with a Bean. This configures CORS globally | 3960 | 0 | 3960 | June 15, 2022 6:41 PM
Improve Logout functionality with a Filter an then call the controller | 2022-06-15 | 2022-06-15 | Sprint 01 | High | Task 🔨 | Cancelled | June 15, 2022 2:00 | June 15, 2022 18:40 | 7 |  | 60000 | 25200 | 34800 | June 15, 2022 2:11 AM
When receiving a request, check if the token exists in DB | 2022-06-16 |  | Sprint 01 | High | Task 🔨 | Not Started | June 16, 2022 18:00 |  |  |  |  | 0 | 0 | June 15, 2022 2:36 PM
Remove Service’s interfaces | 2022-06-17 | 2022-06-17 | Sprint 01 | High | Refactor 🛠️ | Complete | June 17, 2022 14:00 | June 17, 2022 14:17 | 0 |  | 1020 | 0 | 1020 | June 17, 2022 2:16 PM
Migration from Timestamp to LocalDateTime | 2022-06-17 | 2022-06-17 | Sprint 01 | Medium | Refactor 🛠️ | Cancelled | June 17, 2022 15:45 | June 17, 2022 15:50 | 0 | Made with IntelliJ UI JPA Inspector. Returned to Timestamp because Jackson cannot make correct bindings for that type | 300 | 0 | 300 | June 17, 2022 3:54 PM
Document - Requirements specification | 2022-06-20 | 2022-06-20 | Sprint 01 | High | Documentation 📘, Initialization 🎉 | Complete | June 20, 2022 14:00 | June 20, 2022 20:23 | 2 |  | 22980 | 7200 | 15780 | June 14, 2022 2:57 AM
Register page and switch between Login and Register | 2022-06-20 | 2022-06-20 | Sprint 01 | High | Task 🔨 | Complete | June 20, 2022 20:26 | June 20, 2022 20:45 | 0 |  | 1140 | 0 | 1140 | June 20, 2022 8:25 PM
Theme switcher and color palette | 2022-06-20 | 2022-06-20 | Sprint 01 | Low | Task 🔨 | Complete | June 20, 2022 20:36 | June 20, 2022 21:03 | 0 |  | 1620 | 0 | 1620 | June 20, 2022 8:36 PM
Store, Reducers and Actions for Redux | 2022-06-20 | 2022-06-20 | Sprint 01 | High | Task 🔨 | Complete | June 20, 2022 20:41 | June 20, 2022 20:50 | 0 |  | 540 | 0 | 540 | June 20, 2022 8:41 PM
Toolbar with theme switcher | 2022-06-20 | 2022-06-20 | Sprint 01 | Critical 🔥 | Task 🔨 | Complete | June 20, 2022 20:55 | June 20, 2022 21:03 | 0 |  | 480 | 0 | 480 | June 20, 2022 8:55 PM
Backend register functionality | 2022-06-20 | 2022-06-24 | Sprint 01 | Critical 🔥 | Task 🔨 | Complete | June 20, 2022 21:15 | June 24, 2022 22:05 | 26 |  | 348600 | 93600 | 255000 | June 20, 2022 9:54 PM
Configure deploy functionality | 2022-06-21 | 2022-06-22 | Sprint 01 | Critical 🔥 | Initialization 🎉, Task 🔨 | Complete | June 21, 2022 13:00 | June 22, 2022 1:46 | 3 |  | 45960 | 10800 | 35160 | June 21, 2022 6:57 PM
Better configuration of deployment CORS config | 2022-06-22 | 2022-06-23 | Sprint 01 | Critical 🔥 | Task 🔨 | Complete | June 22, 2022 20:30 | June 23, 2022 1:35 | 45047 |  | 18300 | 5400 | 12900 | June 22, 2022 8:32 PM
Migration of frontend to other repo | 2022-06-23 | 2022-06-23 | Sprint 01 | Critical 🔥 | Bug 🐞, Refactor 🛠️, Task 🔨 | Complete | June 23, 2022 0:37 | June 23, 2022 1:35 | 0 |  | 3480 | 0 | 3480 | June 23, 2022 12:42 AM
Improve custom HttpResponse functionality | 2022-06-23 | 2022-06-24 | Sprint 01 | High | Task 🔨 | Complete | June 23, 2022 22:40 | June 24, 2022 3:08 | 0 |  | 16080 | 0 | 16080 | June 23, 2022 10:40 PM
Improve custom HttpRequest functionality | 2022-06-24 | 2022-06-24 | Sprint 01 | High | Task 🔨 | Complete | June 24, 2022 0:05 | June 24, 2022 1:04 | 0 | Little modification was done | 3540 | 0 | 3540 | June 24, 2022 12:04 AM
Refactor Responses with the new class | 2022-06-24 | 2022-06-24 | Sprint 01 | Medium | Refactor 🛠️, Task 🔨 | Complete | June 24, 2022 22:00 | June 24, 2022 22:33 | 0 |  | 1980 | 0 | 1980 | June 24, 2022 7:07 PM
Solve problem with Instant class of the domain models | 2022-06-24 | 2022-06-24 | Sprint 01 | High | Bug 🐞, Refactor 🛠️ | Complete | June 24, 2022 22:45 | June 24, 2022 23:15 | 0.25 | ObjectMapper must have JavaTimeModule registered | 1800 | 900 | 900 | June 24, 2022 10:10 PM
App renaming | 2022-06-24 | 2022-06-25 | Sprint 01 | High | Refactor 🛠️ | Complete | June 24, 2022 23:54 | June 25, 2022 0:15 | 0 |  | 1260 | 0 | 1260 | June 24, 2022 11:54 PM
Frontend API url change when code is in production or in development env | 2022-06-25 | 2022-06-25 | Sprint 01 | High | Bug 🐞, Refactor 🛠️ | Complete | June 25, 2022 0:30 | June 25, 2022 0:50 | 0 |  | 1200 | 0 | 1200 | June 25, 2022 12:54 AM
Improve request handling in filters. Put data in some attribute in the custom class instead of request.setAttribute() | 2022-06-25 | 2022-06-25 | Sprint 01 | High | Refactor 🛠️, Task 🔨 | Complete | June 25, 2022 15:00 | June 25, 2022 15:20 | 0 |  | 1200 | 0 | 1200 | June 25, 2022 3:08 PM
Show all opened sessions of user in profile view | 2022-06-26 | 2022-06-26 | Sprint 01 | Medium | Task 🔨 | Complete | June 26, 2022 0:50 | June 26, 2022 1:15 | 0 |  | 1500 | 0 | 1500 | June 25, 2022 11:53 PM
Profile page with user data (session, name, …) | 2022-06-26 | 2022-07-10 | Sprint 01 | High | Task 🔨 | Complete | June 26, 2022 23:30 | July 17, 2022 0:04 | -1 |  | 1730040 | 0 | 1730040 | June 25, 2022 11:50 PM
Make a Router class to configure HTTP methods and permissions | 2022-06-27 | 2022-06-27 | Sprint 01 | Low | Task 🔨 | Cancelled | June 27, 2022 11:26 | June 27, 2022 11:29 | 0 |  | 180 | 0 | 180 | June 27, 2022 11:26 AM
Add support for all types of files (text, images, videos, audios) | 2022-08-01 | 2022-08-03 | Sprint 02 | Medium | Task 🔨 | Complete | August 1, 2022 23:18 | August 3, 2022 0:05 | 18 | Added a builder for comfort, generalized filetype query to S3 | 89220 | 64800 | 24420 | August 1, 2022 11:18 PM
Spinner on login or register, to know that the request has been sent | 2022-08-11 | 2022-08-11 | Sprint 02 | Medium | Improvement 🚀 | Complete | August 11, 2022 23:00 | August 11, 2022 23:40 | 0 |  | 2400 | 0 | 2400 | August 9, 2022 5:46 PM
New messages when user joins and leaves a chat | 2022-08-03 | 2022-08-04 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Cancelled | August 3, 2022 20:15 | August 4, 2022 22:30 |  | Decided to rollback to the working implementation (create a socket per chat connection) | 94500 | 0 | 94500 | August 3, 2022 8:35 PM
Update docs | 2022-08-05 | 2022-08-07 | Sprint 02 | Very high | Documentation 📘 | Complete | August 5, 2022 19:50 | August 7, 2022 17:52 |  |  | 165720 | 0 | 165720 | July 31, 2022 6:05 PM
Check token on connect to websocket | 2022-08-05 | 2022-08-15 | Sprint 02 | Medium | Improvement 🚀, Security 🔒, Task 🔨 | Revision | August 5, 2022 20:30 | August 15, 2022 17:04 | -1 |  | 851640 | 0 | 851640 | July 31, 2022 5:23 PM
Create updated entities in JPA | 2022-08-05 | 2022-08-06 | Sprint 02 | High | Task 🔨 | Complete | August 5, 2022 22:15 | August 6, 2022 23:26 | 12 | Check if the entities can contain only the reference object, not the id and the object (see Session last 2 attributes). Update: entities only have the id (if an object of other entity is required) | 90660 | 43200 | 47460 | August 5, 2022 11:52 PM
Make administrator view in frontend | 2022-08-06 | 2022-09-13 | Sprint 02 | Medium | Improvement 🚀, Task 🔨 | Complete | August 6, 2022 12:30 | September 13, 2022 13:42 | -1 | Implementation of services | 3287520 | 0 | 3287520 | August 6, 2022 11:48 AM
Make separate classes for Route constants (GET, POST, …) | 2022-08-06 | 2022-08-06 | Sprint 02 | Low | Refactor 🛠️ | Complete | August 6, 2022 14:26 | August 6, 2022 16:14 | 45047 |  | 6480 | 5400 | 1080 | August 6, 2022 2:25 PM
Implement Degree controller and associated Service in backend | 2022-08-06 | 2022-08-06 | Sprint 02 | High | Task 🔨 | Revision | August 6, 2022 16:45 | August 6, 2022 20:48 | 0.3 |  | 14580 | 1080 | 13500 | August 6, 2022 5:20 PM
Update old methods that used ResponseEntity<?> to use the new HttpResponse class | 2022-08-06 | 2022-08-06 | Sprint 02 | Low | Improvement 🚀, Refactor 🛠️ | Complete | August 6, 2022 23:29 | August 6, 2022 23:42 | 0 |  | 780 | 0 | 780 | August 6, 2022 5:31 PM
Check that all routes have the correct http method and permissions | 2022-08-07 | 2022-08-07 | Sprint 02 | High | Task 🔨 | Complete | August 7, 2022 16:53 | August 7, 2022 17:32 | 0 |  | 2340 | 0 | 2340 | August 7, 2022 4:48 PM
Document - Design model | 2022-08-09 | 2022-08-09 | Sprint 02 | High | Documentation 📘, Initialization 🎉 | Complete | August 9, 2022 19:50 | August 9, 2022 20:15 | 0 |  | 1500 | 0 | 1500 | June 14, 2022 3:01 AM
Domain diagram | 2022-08-09 | 2022-08-09 | Sprint 02 | High | Documentation 📘 | Revision | August 9, 2022 22:10 | August 9, 2022 22:30 | 0 | 13-08-22 > It has changes (add groups) | 1200 | 0 | 1200 | August 9, 2022 10:02 PM
Use case diagram | 2022-08-09 | 2022-08-11 | Sprint 02 | High | Documentation 📘 | Revision | August 9, 2022 23:15 | August 11, 2022 22:58 | 18 |  | 171780 | 64800 | 106980 | August 9, 2022 9:52 PM
Add custom Drop Down, password reset and more info in profile | 2022-07-16 | 2022-07-17 | Sprint 02 | High | Task 🔨 | Complete | July 16, 2022 22:04 | July 17, 2022 0:05 | 0 |  | 7260 | 0 | 7260 | July 16, 2022 10:03 PM
Basic chat page | 2022-07-19 | 2022-07-19 | Sprint 02 | High | Task 🔨 | Complete | July 19, 2022 17:00 | July 19, 2022 23:50 | 45047 |  | 24600 | 5400 | 19200 | July 19, 2022 4:55 PM
More style to chat and messages | 2022-07-20 | 2022-07-20 | Sprint 02 | Medium | Task 🔨 | Complete | July 20, 2022 17:55 | July 20, 2022 23:55 | 2 | Messages are broken in several lines if long | 21600 | 7200 | 14400 | July 20, 2022 5:53 PM
Add a new table in DB (Chats) | 2022-07-21 | 2022-07-21 | Sprint 02 | Critical 🔥 | Task 🔨 | Complete | July 21, 2022 17:20 | July 21, 2022 19:06 | 0.5 |  | 6360 | 1800 | 4560 | July 21, 2022 12:06 AM
Move header of message up one component (to ChatMessage.jsx) | 2022-07-21 | 2022-07-21 | Sprint 02 | Medium | Task 🔨 | Complete | July 21, 2022 19:27 | July 21, 2022 19:47 | 0 |  | 1200 | 0 | 1200 | July 21, 2022 7:29 PM
Send messages from front to back | 2022-07-21 | 2022-07-21 | Sprint 02 | High | Task 🔨 | Complete | July 21, 2022 19:55 | July 21, 2022 21:18 | 1 | 1 hour interrupted, I was updating the security routes in a separate class. | 4980 | 3600 | 1380 | July 21, 2022 12:03 AM
Update security of the routes. Make a separate class or something | 2022-07-21 | 2022-07-21 | Sprint 02 | Low | Refactor 🛠️, Task 🔨 | Complete | July 21, 2022 20:00 | July 21, 2022 20:57 | 0 |  | 3420 | 0 | 3420 | July 21, 2022 8:11 PM
Read messages in backend | 2022-07-21 | 2022-07-21 | Sprint 02 | High | Task 🔨 | Complete | July 21, 2022 21:20 | July 21, 2022 21:30 | 0 |  | 600 | 0 | 600 | July 21, 2022 12:03 AM
Store messages in a file with history | 2022-07-21 | 2022-07-21 | Sprint 02 | High | Task 🔨 | Complete | July 21, 2022 22:00 | July 21, 2022 23:30 | 0.4 |  | 5400 | 1440 | 3960 | July 21, 2022 12:03 AM
When sending an empty message, write nothing in the response | 2022-07-23 | 2022-07-23 | Sprint 02 | Critical 🔥 | Refactor 🛠️, Task 🔨 | Complete | July 23, 2022 17:40 | July 23, 2022 17:47 | 0 |  | 420 | 0 | 420 | July 23, 2022 5:41 PM
Create WebSocket server | 2022-07-23 | 2022-07-24 | Sprint 02 | High | Task 🔨 | Complete | July 23, 2022 20:15 | July 24, 2022 1:12 | 45047 |  | 17820 | 5400 | 12420 | July 23, 2022 8:22 PM
Send messages to other members of the chat | 2022-07-24 | 2022-07-26 | Sprint 02 | Critical 🔥 | Task 🔨 | Complete | July 24, 2022 14:48 | July 26, 2022 1:28 | 14 |  | 124800 | 50400 | 74400 | July 21, 2022 10:27 PM
Configure frontend to send messages. Create class and Hook | 2022-07-25 | 2022-07-26 | Sprint 02 | High | Task 🔨 | Complete | July 25, 2022 19:34 | July 26, 2022 0:34 | 45108 |  | 18000 | 6120 | 11880 | July 25, 2022 7:34 PM
Receive messages in frontend from other clients and log to console | 2022-07-26 | 2022-07-26 | Sprint 02 | High | Task 🔨 | Complete | July 26, 2022 0:30 | July 26, 2022 1:28 | 0 | Received and printed in class, not component | 3480 | 0 | 3480 | July 26, 2022 12:29 AM
Add the sessionId when sending the response to the client | 2022-07-26 | 2022-07-26 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Complete | July 26, 2022 16:37 | July 26, 2022 17:30 | 0.25 | Previously it was sent the date of sign in | 3180 | 900 | 2280 | July 26, 2022 4:37 PM
Improve message handling between front and back | 2022-07-26 | 2022-07-26 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Complete | July 26, 2022 18:20 | July 26, 2022 21:28 | 0.6 |  | 11280 | 2160 | 9120 | July 26, 2022 9:19 PM
Clear the sensitive headers to send the received message to other clients in backend | 2022-07-26 | 2022-07-26 | Sprint 02 | Critical 🔥 | Refactor 🛠️, Task 🔨 | Complete | July 26, 2022 18:22 | July 26, 2022 18:38 | 0 |  | 960 | 0 | 960 | July 26, 2022 6:19 PM
Improve storage of clients in backend | 2022-07-26 | 2022-07-27 | Sprint 02 | High | Task 🔨 | Complete | July 26, 2022 22:52 | July 27, 2022 0:32 | 0.6 | WSClientID record was created | 6000 | 2160 | 3840 | July 26, 2022 10:51 PM
Check the date in which the message was sent, to write correctly to the file | 2022-07-27 | 2022-07-27 | Sprint 02 | Critical 🔥 | Bug 🐞, Task 🔨 | Complete | July 27, 2022 0:26 | July 27, 2022 0:29 | 0 |  | 180 | 0 | 180 | July 21, 2022 12:19 AM
Receive message in component | 2022-07-27 | 2022-07-27 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Complete | July 27, 2022 0:48 | July 27, 2022 2:07 | 0 |  | 4740 | 0 | 4740 | July 27, 2022 2:06 AM
Make a record class to identify the WS user in backend | 2022-07-27 | 2022-07-27 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Complete | July 27, 2022 17:57 | July 27, 2022 18:42 | 0 |  | 2700 | 0 | 2700 | July 27, 2022 6:15 PM
Show incoming messages in ChatBox | 2022-07-27 | 2022-07-28 | Sprint 02 | High | Task 🔨 | Complete | July 27, 2022 20:30 | July 28, 2022 16:55 | 14 | 1 - Only shows the last message received 2 - I lasted 6 minutes the following day after watching how to use prevState in setter | 73500 | 50400 | 23100 | July 27, 2022 8:30 PM
Provide more style to message components | 2022-07-28 | 2022-07-28 | Sprint 02 | High | Improvement 🚀, Task 🔨 | Complete | July 28, 2022 17:05 | July 28, 2022 20:33 | 0.8 | Can be updated anytime | 12480 | 2880 | 9600 | July 28, 2022 7:52 PM
Make a deploy test in Heroku, to verify the functionality of the sockets | 2022-07-28 | 2022-08-05 | Sprint 02 | High | Research ⛰️ | Complete | July 28, 2022 17:42 | August 5, 2022 0:45 | -1 | Working with S3 correctly, remains connecting to available chats, not the one you want | 630180 | 0 | 630180 | July 26, 2022 12:51 PM
Migrate from Java-WebSocket lib to Jetty websockets in backend | 2022-07-29 | 2022-07-30 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Complete | July 29, 2022 21:03 | July 30, 2022 15:59 | 14 | Tested with an auxiliary file in frontend | 68160 | 50400 | 17760 | July 29, 2022 9:02 PM
Migrate from native WebSocket to websocket library in frontend | 2022-07-30 | 2022-07-30 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Cancelled | July 30, 2022 16:05 | July 30, 2022 17:31 |  | I can use the native WebSocket. 1.5 hours lost 😢 | 5160 | 0 | 5160 | July 29, 2022 9:01 PM
Migrate backend to spring websocket support with custom Handlers | 2022-07-30 | 2022-07-31 | Sprint 02 | High | Refactor 🛠️, Task 🔨 | Complete | July 30, 2022 18:42 | July 31, 2022 15:00 | 10 | Client is receiving 403 code from the server | 73080 | 36000 | 37080 | July 30, 2022 6:42 PM
Better handling of chats with a new class | 2022-07-31 | 2022-07-31 | Sprint 02 | Low | Refactor 🛠️ | Complete | July 31, 2022 15:45 | July 31, 2022 17:22 | 0 |  | 5820 | 0 | 5820 | July 31, 2022 5:21 PM
Add a Writer to support message storage in S3. Upload files | 2022-07-31 | 2022-07-31 | Sprint 02 | High | Improvement 🚀, Task 🔨 | Complete | July 31, 2022 19:55 | July 31, 2022 20:05 | 0 |  | 600 | 0 | 600 | July 31, 2022 5:26 PM
When uploading file (finished chat) delete from disk. If chat is reopened, download file and keep writting | 2022-07-31 | 2022-08-01 | Sprint 02 | Medium | Improvement 🚀, Task 🔨 | Complete | July 31, 2022 20:06 | August 1, 2022 23:05 | 20 | Key to check for existence was invalid (.txt was not added to the search which returned false) | 97140 | 72000 | 25140 | July 31, 2022 8:05 PM
Check migration guide java-jwt to version 4 | 2022-08-12 | 2022-08-12 | Sprint 03 | Low | Security 🔒 | Complete | August 12, 2022 20:43 | August 12, 2022 23:56 | 45048 |  | 11580 | 9000 | 2580 | August 5, 2022 8:57 PM
Decide chat type names | 2022-08-13 | 2022-08-13 | Sprint 03 | High | Refactor 🛠️ | Revision | August 13, 2022 0:11 | August 13, 2022 0:30 | 0 |  | 1140 | 0 | 1140 | August 13, 2022 12:10 AM
Decide structure of the chat URLs | 2022-08-13 | 2022-08-13 | Sprint 03 | Very high | Task 🔨 | May change | August 13, 2022 0:30 | August 13, 2022 1:00 | 0 |  | 1800 | 0 | 1800 | August 13, 2022 12:39 AM
Add groups to all diagrams | 2022-08-13 | 2022-08-13 | Sprint 03 | Critical 🔥 | Task 🔨 | Complete | August 13, 2022 0:45 | August 13, 2022 14:05 | 12 |  | 48000 | 43200 | 4800 | August 13, 2022 12:59 AM
How to escape SQL reserved keywords with Spring boot, JPA and Hibernate - Java JEE tutorials by Tarik Chrouki | 2022-08-14 | 2022-08-14 | Sprint 03 | High | Bug 🐞 | Complete | August 14, 2022 17:40 | August 14, 2022 17:45 | 0 |  | 300 | 0 | 300 | August 14, 2022 5:50 PM | [5 empty] | https://www.chrouki.com/posts/escape-sql-reserved-keywords-jpa-hibernate/
Show available chats to user in home view | 2022-08-15 | 2022-08-15 | Sprint 03 | High | Task 🔨 | Complete | August 15, 2022 19:33 | August 15, 2022 23:05 | 45017 | See Home page with chat selection (https://www.notion.so/Home-page-with-chat-selection-21ecf1ef88a44884807c4e91b67ac002?pvs=21) | 12720 | 5040 | 7680 | August 15, 2022 7:35 PM
Make chatReducer to shorten loading of home screen when requesting all available chats for a user | 2022-08-16 | 2022-08-16 | Sprint 03 | High | Improvement 🚀, Task 🔨 | Complete | August 16, 2022 16:55 | August 16, 2022 17:36 | 0 | Added the request of all the chats on login and return to client. | 2460 | 0 | 2460 | August 16, 2022 4:40 PM
Add a callback to client to execute it when a message is sent correctly | 2022-08-16 | 2022-08-16 | Sprint 03 | Low | Refactor 🛠️ | Complete | August 16, 2022 17:41 | August 16, 2022 17:58 | 0 |  | 1020 | 0 | 1020 | August 16, 2022 4:35 PM
Change type of chat in DB to longer name | 2022-08-16 | 2022-08-17 | Sprint 03 | High | Refactor 🛠️ | Complete | August 16, 2022 20:56 | August 17, 2022 22:30 | 1 | Also changed metadata column to json type | 92040 | 3600 | 88440 | August 16, 2022 8:56 PM
Fix problems adding users to global chat on register | 2022-08-17 | 2022-08-17 | Sprint 03 | Very high | Bug 🐞 | Complete | August 17, 2022 20:32 | August 17, 2022 23:20 | 0.75 | IMPORTANT: PK classes are now @Embeddable and they are used in related entity class as a private field with the annotation @EmbeddedId | 10080 | 2700 | 7380 | August 17, 2022 8:31 PM
Improve chat with name and more information about it | 2022-08-18 | 2022-08-18 | Sprint 03 | High | Task 🔨 | May change | August 18, 2022 19:15 | August 18, 2022 20:19 | 0.25 |  | 3840 | 900 | 2940 | August 18, 2022 7:14 PM
Divide each DropDown into new component and include them in Administration view | 2022-08-18 | 2022-08-19 | Sprint 03 | Medium | Refactor 🛠️ | Complete | August 18, 2022 20:22 | August 19, 2022 0:15 | 45047 | Made in 2 phases (Extraction, Refactoring). Also extracted Dialogs to new components | 13980 | 5400 | 8580 | August 13, 2022 11:00 PM
Edit diagrams and refactor entity classes (relation classes) and SQL definition to make columns match the table name | 2022-08-19 | 2022-08-19 | Sprint 03 | Very high | Bug 🐞, Refactor 🛠️ | Complete | August 19, 2022 16:41 | August 19, 2022 17:18 | 0 |  | 2220 | 0 | 2220 | August 19, 2022 4:41 PM
Listen to new messages and check if they are USER_JOINED or USER_LEFT and send a new type of message to get the connected users of the chat in the background | 2022-08-19 | 2022-08-20 | Sprint 03 | Medium | Improvement 🚀 | Complete | August 19, 2022 22:00 | August 20, 2022 0:17 | 0 | Use ACTIVE_USERS_MESSAGE | 8220 | 0 | 8220 | August 18, 2022 8:14 PM
Add a list of connected users to the chat view | 2022-08-19 | 2022-08-20 | Sprint 03 | Very low | Idea 🧠, Improvement 🚀 | Complete | August 19, 2022 22:37 | August 20, 2022 0:13 | 0 |  | 5760 | 0 | 5760 | August 18, 2022 7:15 PM
Show popup when hovering hour of message to display full date | 2022-08-21 | 2022-08-21 | Sprint 03 | High | Improvement 🚀 | Complete | August 21, 2022 19:26 | August 21, 2022 20:00 | 0 | Also added dateformat lib. See Show popup when hovering hour of message to display full date (https://www.notion.so/Show-popup-when-hovering-hour-of-message-to-display-full-date-3d4c7f0eab454e48926ec30711919d6a?pvs=21) | 2040 | 0 | 2040 | August 21, 2022 7:25 PM
Use strategy pattern to make MessageHandler more readable | 2022-08-22 | 2022-08-22 | Sprint 03 | Very high | Refactor 🛠️ | Complete | August 22, 2022 0:16 | August 22, 2022 20:47 | 15 |  | 73860 | 54000 | 19860 | August 22, 2022 12:14 AM
Upon connection of the user, receive all the messages of the chat up to a limit of 3 days before | 2022-08-22 | 2022-08-22 | Sprint 03 | High | Improvement 🚀 | Complete | August 22, 2022 20:49 | August 22, 2022 23:48 | 0.75 | New message type. Messages are sent after the listeners are set | 10740 | 2700 | 8040 | August 21, 2022 11:25 PM
Read history from file stored in disk if it is downloaded. To have updated history to new users | 2022-08-23 | 2022-08-24 | Sprint 03 | Critical 🔥 | Bug 🐞, Refactor 🛠️ | Complete | August 23, 2022 18:00 | August 24, 2022 1:00 | 2 | Since it is always downloaded when the first user is connected, if more users connect to the chat, it is only needed to read from the file | 25200 | 7200 | 18000 | August 23, 2022 8:45 PM
Order active users by name | 2022-08-23 | 2022-08-23 | Sprint 03 | Low | Improvement 🚀 | Complete | August 23, 2022 20:25 | August 23, 2022 20:34 | 0 |  | 540 | 0 | 540 | August 22, 2022 11:52 PM
Schedule the upload of the history file to S3 after a period of time | 2022-08-24 | 2022-08-24 | Sprint 03 | High | Improvement 🚀 | Reference | August 24, 2022 20:30 | August 24, 2022 20:50 | 0 | See Upload the file to S3 every 10 minutes (https://www.notion.so/Upload-the-file-to-S3-every-10-minutes-e9a76afa190a45e7ac3916b266926a2c?pvs=21) | 1200 | 0 | 1200 | August 23, 2022 9:06 PM
Upload the file to S3 every 10 minutes | 2022-08-24 | 2022-08-24 | Sprint 03 | Medium | Improvement 🚀, Task 🔨 | Revision | August 24, 2022 20:30 | August 24, 2022 20:50 | 0 | Do this if a chat has clients for this amount of time | 1200 | 0 | 1200 | July 21, 2022 12:04 AM
Do the documentation of the Java code | 2022-08-24 | 2022-08-26 | Sprint 03 | Very high | Documentation 📘 | Complete | August 24, 2022 22:47 | August 26, 2022 0:40 | 12 |  | 93180 | 43200 | 49980 | August 23, 2022 1:14 AM
Add the README.md | 2022-08-26 | 2022-08-26 | Sprint 03 | Low | Documentation 📘 | Complete | August 26, 2022 19:05 | August 26, 2022 21:00 | 0.2 | Added file to frontend and backend | 6900 | 720 | 6180 | August 26, 2022 7:14 PM
Add drag ‘n’ drop to select files to send to the chat | 2022-08-26 | 2022-08-27 | Sprint 03 | High | Task 🔨 | Complete | August 26, 2022 20:50 | August 27, 2022 15:00 | 12 |  | 65400 | 43200 | 22200 | August 26, 2022 11:20 PM
Add support to encode (in base64) files to be able to send to the server as normal WebSocket messages | 2022-08-26 | 2022-08-26 | Sprint 03 | High | Task 🔨 | Complete | August 26, 2022 22:50 | August 26, 2022 23:20 | 0 | They are sent as HTTP requests, not through WebSocket, since there is a data size limit. See Upload images from frontend with drag ’n’ drop and encode into base64 (https://www.notion.so/Upload-images-from-frontend-with-drag-n-drop-and-encode-into-base64-c909e17c0d3b44069d511f5dcd53aea8?pvs=21) | 1800 | 0 | 1800 | August 26, 2022 11:24 PM
Send the media files with http requests to the server instead of encoding and sending through the WebSocket | 2022-08-27 | 2022-08-27 | Sprint 03 | Very high | Improvement 🚀, Refactor 🛠️ | Complete | August 27, 2022 14:30 | August 27, 2022 23:45 | 45047 | Improvement for https://www.notion.so/Add-support-to-encode-in-base64-files-to-be-able-to-send-to-the-server-as-normal-WebSocket-message-546530de3be44c8fb35446656946971e?pvs=21 task, since through WebSockets the data transmission is limited to few kB. | 33300 | 5400 | 27900 | August 27, 2022 2:32 PM
Migrate maxWidth determination to backend | 2022-08-28 | 2022-08-28 | Sprint 03 | Low | Refactor 🛠️ | Complete | August 28, 2022 20:43 | August 28, 2022 20:55 | 0 |  | 720 | 0 | 720 | August 28, 2022 8:40 PM
Add functionality for adding more media files | 2022-08-28 | 2022-09-02 | Sprint 03 | Very high | Task 🔨 | Complete | August 28, 2022 23:15 | September 2, 2022 17:34 | -1 | Another Strategy pattern in FileController | 411540 | 0 | 411540 | August 28, 2022 9:01 PM
Fix url when receiving response from server | 2022-08-28 | 2022-08-29 | Sprint 03 | Critical 🔥 | Bug 🐞 | Complete | August 28, 2022 23:19 | August 29, 2022 0:40 | 0 |  | 4860 | 0 | 4860 | August 28, 2022 11:19 PM
Change all TextField components to be size=’small’ | 2022-09-10 | 2022-09-11 | Sprint 03 | Low | Refactor 🛠️ | Complete | September 10, 2022 20:49 | September 11, 2022 20:55 | 0 |  | 86760 | 0 | 86760 | September 10, 2022 12:49 AM
Add support for having database in localhost | 2022-09-02 | 2022-09-02 | Sprint 03 | High | Task 🔨 | Complete | September 2, 2022 18:45 | September 2, 2022 18:56 | 0 |  | 660 | 0 | 660 | September 2, 2022 6:53 PM
Send a ping message from frontend to keep the connection alive | 2022-09-04 | 2022-09-04 | Sprint 03 | Critical 🔥 | Task 🔨 | Complete | September 4, 2022 23:00 | September 4, 2022 23:27 | 0 |  | 1620 | 0 | 1620 | September 2, 2022 1:47 PM
Migrate applications from Heroku to Vercel | 2022-09-05 | 2022-09-05 | Sprint 03 | High | Task 🔨 | Complete | September 5, 2022 23:00 | September 5, 2022 23:15 | 0 | Only frontend was moved. Heroku will not have free plans after 28th November 2022. Contact Vercel if they have student plans | 900 | 0 | 900 | September 2, 2022 8:12 PM
Disable send button if no text or image is going to be sent | 2022-09-06 | 2022-09-06 | Sprint 03 | Low | Improvement 🚀, Task 🔨 | Complete | September 6, 2022 1:00 | September 6, 2022 1:50 | 0 |  | 3000 | 0 | 3000 | September 6, 2022 1:50 AM
Show how many images are attached to the message | 2022-09-06 | 2022-09-06 | Sprint 03 | Low | Improvement 🚀, Task 🔨 | Complete | September 6, 2022 1:20 | September 6, 2022 1:40 | 0 | They must be confirmed in the dialog. If the dialog is closed without clicking on the “Attach” button, the files will remain selected but the user cannot send the message. After sending a message, if images were selected but not attached, they are removed from the selection. | 1200 | 0 | 1200 | September 6, 2022 1:48 AM
Be able to handle several files at once, to keep the order in which they were sent | 2022-09-06 | 2022-09-06 | Sprint 03 | Medium | Improvement 🚀 | Complete | September 6, 2022 1:45 | September 6, 2022 3:00 | 0 |  | 4500 | 0 | 4500 | September 6, 2022 2:11 AM
Make a Feature readme file | 2022-09-06 | 2022-09-07 | Sprint 03 | Very high | Documentation 📘 | Complete | September 6, 2022 20:00 | September 7, 2022 0:13 | 2 |  | 15180 | 7200 | 7980 | September 7, 2022 12:12 AM
Idle connection of WebSockets | 2022-09-07 | 2022-09-07 | Sprint 03 | Critical 🔥 | Bug 🐞 | Complete | September 7, 2022 14:22 | September 7, 2022 17:00 | 1 | Needs to be tested. Solved by adding an interval | 9480 | 3600 | 5880 | August 29, 2022 12:09 AM
Create invitation links to put in profile and join a chat | 2022-09-07 | 2022-09-07 | Sprint 03 | Very high | Improvement 🚀, Task 🔨 | Complete | September 7, 2022 17:31 | September 7, 2022 20:56 | 45047 | Add new column in chat table. They are codes, not links (for the moment) | 12300 | 5400 | 6900 | August 18, 2022 8:20 PM
Add style to have chats structured in a grid in Home view | 2022-09-07 | 2022-09-08 | Sprint 03 | High | Improvement 🚀, Task 🔨 | Complete | September 7, 2022 21:12 | September 8, 2022 2:10 | 45047 |  | 17880 | 5400 | 12480 | September 7, 2022 9:11 PM
Extract to a JSON the router structure in App component | 2022-09-08 | 2022-09-08 | Sprint 03 | High | Refactor 🛠️ | Complete | September 8, 2022 16:11 | September 8, 2022 16:54 | 0 | Make an array of objects that have: path, type (public, private or admin), component. If public, add restricted or not | 2580 | 0 | 2580 | September 8, 2022 4:10 PM
Remove express and file to serve frontend (since Vercel does not need it) | 2022-09-08 | 2022-09-08 | Sprint 03 | Very high | Refactor 🛠️ | Complete | September 8, 2022 17:06 | September 8, 2022 17:10 | 0 | Vercel uses package.json file | 240 | 0 | 240 | September 7, 2022 3:00 AM
When entering a chat, send a http request to check if the user has access to that chat | 2022-09-08 | 2022-09-08 | Sprint 03 | Very high | Task 🔨 | Complete | September 8, 2022 17:23 | September 8, 2022 19:59 | 0.5 | This is done to prevent users to join a chat that is not available to them (modify the URL by hand). See also Restrict the connection to chats. Users can only connect to available ones (https://www.notion.so/Restrict-the-connection-to-chats-Users-can-only-connect-to-available-ones-84c5c82861bf476a961e7008d52b396a?pvs=21) | 9360 | 1800 | 7560 | August 13, 2022 12:25 AM
Restrict the connection to chats. Users can only connect to available ones | 2022-09-08 | 2022-09-08 | Sprint 03 | Critical 🔥 | Refactor 🛠️, Task 🔨 | Complete | September 8, 2022 17:23 | September 8, 2022 19:59 | 0.5 | See also When entering a chat, send a http request to check if the user has access to that chat (https://www.notion.so/When-entering-a-chat-send-a-http-request-to-check-if-the-user-has-access-to-that-chat-73bb78c5b4594cd494c5254b398df53c?pvs=21) | 9360 | 1800 | 7560 | August 5, 2022 12:50 AM
Configure email sender to be able to send emails when users are registered or password are reset | 2022-09-09 | 2022-09-09 | Sprint 03 | Very high | Improvement 🚀, Task 🔨 | Complete | September 9, 2022 0:05 | September 9, 2022 1:11 | 0.5 |  | 3960 | 1800 | 2160 | September 7, 2022 12:13 AM
Add email templates for register and password change | 2022-09-09 | 2022-09-11 | Sprint 03 | High | Improvement 🚀 | Complete | September 9, 2022 1:20 | September 11, 2022 17:25 | 32 |  | 230700 | 115200 | 115500 | September 9, 2022 1:01 AM
Fix 404 error when accessing app in Vercel from external page | 2022-09-09 | 2022-09-09 | Sprint 03 | High | Bug 🐞, Documentation 📘 | Complete | September 9, 2022 14:00 | September 9, 2022 14:30 | 0 | https://t3.gg/blog/post/vite-vercel | 1800 | 0 | 1800 | September 9, 2022 2:00 PM
If user checks the “Remember me” checkbox, extend the expiration time of the access token to 2 weeks or more | 2022-09-09 | 2022-09-09 | Sprint 03 | High | Improvement 🚀 | Complete | September 9, 2022 20:05 | September 9, 2022 20:27 | 0 |  | 1320 | 0 | 1320 | September 6, 2022 6:17 PM
Implement Forgot password functionality and improve reset password. When the user wants to change the password in the profile, send a forgotPassword request with the email, then redirect to create password, since it will be correct | 2022-09-09 | 2022-09-10 | Sprint 03 | High | Improvement 🚀, Task 🔨 | Complete | September 9, 2022 20:35 | September 10, 2022 3:06 | 44959 | Create a new column in users’ table (Or a composite value (so a new table is created) with password, reset password and a code to generate when it resets or forgets). The last option implies heavier refactoring (finally first option is implemented). See Forgot password functionality (https://www.notion.so/Forgot-password-functionality-94c4623ff12e4c0d8f9b2f675e24d9f3?pvs=21) | 23460 | 7920 | 15540 | September 6, 2022 7:55 PM
Document the pattern used by the ChatMap class | 2022-10-01 | 2022-10-04 | Sprint 04 | High | Documentation 📘 | Complete | October 1, 2022 13:45 | October 4, 2022 12:16 | -1 |  | 253860 | 0 | 253860 | September 21, 2022 8:10 PM
Meeting with David Nkoto from Platform.sh | 2022-10-04 | 2022-10-04 | Sprint 04 | Critical 🔥 | Task 🔨 | Complete | October 4, 2022 11:00 | October 4, 2022 11:20 | 0 | No contract agreed | 1200 | 0 | 1200 | October 3, 2022 6:35 PM
Notification when a message is received | 2022-10-08 | 2022-10-08 | Sprint 04 | Low | Improvement 🚀 | Complete | October 8, 2022 1:36 | October 8, 2022 2:00 | 0 | Source of the notification sound: https://mobcup.net/ringtone/mobile-ah-song-jcpfodv9 | 1440 | 0 | 1440 | September 28, 2022 12:57 PM
Solve problem of not sending USER_LEFT (and USER_JOINED) messages to the server | 2022-09-12 | 2022-09-12 | Sprint 04 | Critical 🔥 | Bug 🐞 | Complete | September 12, 2022 17:15 | September 12, 2022 20:00 | 0.1 | The client was disabled before sending the USER_LEFT message. USER_JOINED are sent after checking that the user can connect to the chat, in the chat page | 9900 | 360 | 9540 | September 12, 2022 6:08 PM
Administrators and teachers must have access to invitation code of a chat | 2022-09-12 | 2022-09-13 | Sprint 04 | High | Improvement 🚀 | Complete | September 12, 2022 23:00 | September 13, 2022 1:00 | 0 | When clicking the chat name or show next to it | 7200 | 0 | 7200 | September 7, 2022 7:37 PM
Fix exception when a user exits a chat. User is not created and added to chat | 2022-09-12 | 2022-09-12 | Sprint 04 | Critical 🔥 | Bug 🐞 | Complete | September 12, 2022 8:35 | September 12, 2022 8:54 | 0 | The connection with the method does not work as expected. The connection is made in the onopen of the WebSocket | 1140 | 0 | 1140 | September 12, 2022 3:31 AM
Improve administration view to have several big buttons to select the next window to visualize (not having all data in the same page) | 2022-09-13 | 2022-09-13 | Sprint 04 | High | Improvement 🚀, Refactor 🛠️ | Complete | September 13, 2022 12:15 | September 13, 2022 13:42 | 0 | Also added Statistics page | 5220 | 0 | 5220 | September 12, 2022 11:21 PM
Save the files uploaded to the database | 2022-09-14 | 2022-09-14 | Sprint 04 | High | Task 🔨 | Complete | September 14, 2022 13:50 | September 14, 2022 14:52 | 0 |  | 3720 | 0 | 3720 | September 14, 2022 1:54 PM
Limit the size of the files uploaded | 2022-09-14 | 2022-09-14 | Sprint 04 | High | Improvement 🚀 | Complete | September 14, 2022 14:52 | September 14, 2022 14:57 | 0 |  | 300 | 0 | 300 | September 14, 2022 1:21 PM
Fix problems with audio files that move one message down | 2022-09-14 | 2022-09-14 | Sprint 04 | Critical 🔥 | Bug 🐞 | Complete | September 14, 2022 16:47 | September 14, 2022 17:24 | 0 | Only fails when the app is executed locally | 2220 | 0 | 2220 | September 14, 2022 4:56 PM
Remove null clients from list in backend when a message is going to be sent | 2022-09-14 | 2022-09-14 | Sprint 04 | Medium | Bug 🐞 | Complete | September 14, 2022 20:04 | September 14, 2022 20:16 | 0 | Made to prevent errors. Every 3 minutes, check if there are null clients in the list. | 720 | 0 | 720 | September 8, 2022 8:04 PM
Refactor the messages sent over WS to remove encoding field (we only use UTF-8), and simplify to UTF8 | 2022-09-15 | 2022-09-15 | Sprint 04 | High | Refactor 🛠️ | Complete | September 15, 2022 12:21 | September 15, 2022 12:33 | 0 |  | 720 | 0 | 720 | September 14, 2022 8:32 PM
Reduce emojis file to only needed fields (name, emoji, unicode, category, sub-category) | 2022-09-15 | 2022-09-15 | Sprint 04 | Medium | Improvement 🚀 | Complete | September 15, 2022 12:36 | September 15, 2022 13:46 | 0 | Make a table for emojis | 4200 | 0 | 4200 | September 14, 2022 9:56 PM
Add the clock (bean) to Instant.now() calls | 2022-09-16 | 2022-09-16 | Sprint 04 | Medium | Task 🔨 | Complete | September 16, 2022 13:26 | September 16, 2022 13:36 | 0 |  | 600 | 0 | 600 | September 16, 2022 1:35 PM
Add support for adding emojis without pasting them (some keyword like ‘:’) | 2022-09-16 | 2022-09-19 | Sprint 04 | Low | Improvement 🚀 | Complete | September 16, 2022 14:03 | September 19, 2022 21:04 | -1 | Api: https://github.com/abourtnik/emojis-world Or have the list in memory or read from the file or have a table in db. Decision: DB. When the users enters character ‘:’ some emojis are suggested. The emoji is between ‘:’ characters | 284460 | 0 | 284460 | September 14, 2022 5:26 PM
Instead of ‘:’ for showing emojis, add a button at the beginning of the TextBox | 2022-09-22 | 2022-10-06 | Sprint 04 | High | Refactor 🛠️ | Complete | September 22, 2022 15:00 | October 6, 2022 20:17 | -1 | Paused the implementation due to creation of the document for the final delivery | 1228620 | 0 | 1228620 | September 20, 2022 9:57 AM
Fix problems with tests | 2022-09-26 | 2022-09-26 | Sprint 04 | Very high | Bug 🐞, Test 🧪 | Complete | September 26, 2022 21:45 | September 26, 2022 22:36 | 0.2 | https://medium.com/@skywalkerhunter/fix-org-h2-jdbc-jdbcsqlexception-schema-not-found-and-why-50debde657fa solves problems. https://community.developer.atlassian.com/t/problem-running-junit5-tests-with-maven-surefire/36792 solves problems running tests with Maven | 3060 | 720 | 2340 | September 26, 2022 10:35 PM
Add some unit and integration tests | 2022-09-27 |  | Sprint 04 | High | Task 🔨, Test 🧪 | In Progress | September 27, 2022 11:30 |  |  |  |  | 0 | 0 | September 27, 2022 12:52 PM
Improve services to throw exceptions if the entity is not found or an error occurs (and not make it in the controller) and other functionality that could be moved from controllers | 2022-09-28 | 2022-10-07 | Sprint 04 | Medium | Refactor 🛠️, Test 🧪 | May change | September 28, 2022 16:20 | October 7, 2022 0:19 | -1 | Needed refactor of Service and Controller classes | 719940 | 0 | 719940 | September 28, 2022 1:16 PM
Refactor message strategy to have only one implementation of handle method (Audio/Image/Text/Video classes) | 2022-09-30 | 2022-09-30 | Sprint 04 | Medium | Refactor 🛠️ | Complete | September 30, 2022 19:48 | September 30, 2022 20:00 | 0 |  | 720 | 0 | 720 | September 30, 2022 8:00 PM
Global variable to store the WebSocket client when the user is logged in | 2022-11-02 | 2022-11-02 | Sprint 05 | High | Improvement 🚀 | Complete | November 2, 2022 16:41 | November 2, 2022 17:00 | 0 | Kept global state with a React context: https://stackoverflow.com/questions/69675357/react-what-is-the-proper-way-to-do-global-state | 1140 | 0 | 1140 | November 2, 2022 4:31 PM
State information about the connection of the socket to the server (Connected or disconnected) in Toolbar | 2022-11-02 | 2022-11-02 | Sprint 05 | Medium | Improvement 🚀 | Complete | November 2, 2022 17:03 | November 2, 2022 17:11 | 0 |  | 480 | 0 | 480 | November 2, 2022 4:57 PM
Extract connection display to new component | 2022-11-04 | 2022-11-04 | Sprint 05 | Medium | Refactor 🛠️ | Complete | November 4, 2022 13:39 | November 4, 2022 14:00 | 0 |  | 1260 | 0 | 1260 | November 4, 2022 8:15 PM
New component colors for the information messages | 2022-11-04 | 2022-11-04 | Sprint 05 | High | Improvement 🚀 | Complete | November 4, 2022 14:21 | November 4, 2022 14:23 | 0 |  | 120 | 0 | 120 | November 4, 2022 1:37 PM
Revise all todo tasks | 2022-11-04 | 2022-11-05 | Sprint 05 | Very high | Research ⛰️, Task 🔨 | Complete | November 4, 2022 20:27 | November 5, 2022 0:58 | 45047 | First frontend, then backend | 16260 | 5400 | 10860 | November 4, 2022 8:26 PM
Add support for commands with ‘/’ character | 2022-11-05 | 2022-11-05 | Sprint 05 | Low | Improvement 🚀 | Complete | November 5, 2022 2:01 | November 5, 2022 15:33 | 9 | Use a Tokenizer (idea) | 48720 | 32400 | 16320 | September 16, 2022 3:11 PM
Support mentions with ‘@’ character | 2022-11-05 | 2022-11-05 | Sprint 05 | Medium | Improvement 🚀 | Complete | November 5, 2022 3:36 | November 5, 2022 15:33 | 9 | Use the same tokenizer for commands but for @ symbol | 43020 | 32400 | 10620 | November 5, 2022 3:34 AM
Implement commands and mentions | 2022-11-06 |  | Sprint 05 | High | Improvement 🚀 | In Progress | November 6, 2022 2:34 |  |  |  |  | 0 | 0 | November 5, 2022 3:34 PM
Fit content to all devices (Phone, tablet, pc) | 2022-10-11 | 2022-10-12 | Sprint 05 | Critical 🔥 | Improvement 🚀, Task 🔨 | Complete | October 11, 2022 23:07 | October 12, 2022 0:29 | 0 |  | 4920 | 0 | 4920 | October 11, 2022 11:06 PM
Published Instagram story to get feedback | 2022-10-12 | 2022-10-13 | Sprint 05 | Medium | Research ⛰️ | Complete | October 12, 2022 0:36 | October 13, 2022 0:36 | 0 |  | 86400 | 0 | 86400 | October 12, 2022 1:37 AM
Register email address in Sendgrid to prevent automatic emails to be received in spam folder | 2022-10-12 |  | Sprint 05 | Very high | Bug 🐞 | TempCancel | October 12, 2022 2:35 |  |  | Emails are received in spam folder 😟. Moved to Gmail (using tricks 😂 by creating account from mobile without adding it) and new implementation. The links are modified and email is sent to spam. |  | 0 | 0 | October 12, 2022 2:37 AM
Infinite requests when going to add new group | 2022-10-12 | 2022-10-12 | Sprint 05 | High | Bug 🐞 | Complete | October 12, 2022 23:24 | October 12, 2022 23:26 | 0 | A dependency list in useEffect was not present | 120 | 0 | 120 | October 12, 2022 11:23 PM
Improve chat grid at home page | 2022-10-13 | 2022-10-13 | Sprint 05 | Very high | Bug 🐞 | Complete | October 13, 2022 0:02 | October 13, 2022 0:22 | 0 | Removed margin from DropDown and must be set whenever it is used to the inner components | 1200 | 0 | 1200 | October 13, 2022 12:02 AM
Improve Active users tab with list switching (active / all) | 2022-10-13 | 2022-10-13 | Sprint 05 | Medium | Improvement 🚀 | Complete | October 13, 2022 15:50 | October 13, 2022 17:34 | 0.5 |  | 6240 | 1800 | 4440 | October 13, 2022 3:54 PM
Configure home server | 2022-10-14 | 2022-10-16 | Sprint 05 | Critical 🔥 | Configuration ⚙️, Improvement 🚀 | Complete | October 14, 2022 16:00 | October 16, 2022 22:00 | 16 |  | 194400 | 57600 | 136800 | October 16, 2022 5:00 PM
Backend works correctly in home server | 2022-10-15 | 2022-10-15 | Sprint 05 | Critical 🔥 | Configuration ⚙️ | Complete | October 15, 2022 20:00 | October 15, 2022 23:15 | 0.7 |  | 11700 | 2520 | 9180 | October 15, 2022 11:15 PM
Make WebSockets work in the home server | 2022-10-15 | 2022-10-15 | Sprint 05 | Critical 🔥 | Configuration ⚙️ | Complete | October 15, 2022 23:28 | October 15, 2022 23:32 | 0 | Only needed to change WebSocket connection URL | 240 | 0 | 240 | October 15, 2022 11:27 PM
Create self-signed SSL cert to enable access from Vercel | 2022-10-16 | 2022-10-17 | Sprint 05 | Very high | Bug 🐞, Configuration ⚙️ | Complete | October 16, 2022 18:32 | October 17, 2022 21:12 | 8 | No self-signed SSL used. We use certbot to get the certificates automatically with reliable CA. | 96000 | 28800 | 67200 | October 16, 2022 6:32 PM
Improve log configuration file to make files with RollingFilePolicy | 2022-10-19 | 2022-10-20 | Sprint 05 | Medium | Improvement 🚀 | Complete | October 19, 2022 17:20 | October 20, 2022 18:10 | 0 |  | 89400 | 0 | 89400 | October 19, 2022 6:04 PM
Improve Administration pages with edit and list views (with edit and remove button on every item of the list) | 2022-10-21 | 2022-10-22 | Sprint 05 | Medium | Improvement 🚀 | Complete | October 21, 2022 19:30 | October 22, 2022 17:23 | 10 | Deleting chats, remove history | 78780 | 36000 | 42780 | October 20, 2022 7:24 PM
Fix removal of chats with incorrect id. Modify tables to have one column with the id of the table the entries come from. | 2022-10-22 | 2022-10-22 | Sprint 05 | High | Bug 🐞 | Complete | October 22, 2022 12:15 | October 22, 2022 23:45 | 3 |  | 41400 | 10800 | 30600 | October 22, 2022 1:07 PM
Check why the sessions are removed every time the scheduled task is executed | 2022-10-25 | 2022-10-25 | Sprint 05 | Medium | Bug 🐞 | Complete | October 25, 2022 20:25 | October 25, 2022 20:32 | 0 | Token did not have the prefix when verifying it. Changed implementation of the method to support having or not the “Bearer “ prefix | 420 | 0 | 420 | October 25, 2022 3:12 AM
Add support for text and pdf files messages | 2022-10-26 | 2022-10-26 | Sprint 05 | High | Improvement 🚀 | Complete | October 26, 2022 0:38 | October 26, 2022 1:30 | 0 | Remains giving style to the message boxes | 3120 | 0 | 3120 | October 26, 2022 12:38 AM
PDF visualizer | 2022-10-26 | 2022-10-26 | Sprint 05 | Medium | Improvement 🚀 | Complete | October 26, 2022 15:30 | October 26, 2022 17:38 | 0.3 |  | 7680 | 1080 | 6600 | October 25, 2022 8:41 PM
Leave chat (user action) | 2022-10-26 | 2022-10-26 | Sprint 05 | Medium | Improvement 🚀 | Complete | October 26, 2022 18:53 | October 26, 2022 19:10 | 0 |  | 1020 | 0 | 1020 | October 26, 2022 6:45 PM
Improve performance when showing the emojis | 2022-10-26 |  | Sprint 05 | Very high | Improvement 🚀 | In Progress | October 26, 2022 19:38 |  |  |  |  | 0 | 0 | October 23, 2022 1:21 PM
When clicking a username in a chat, display a small popup with a button to start a user-user chat or other actions | 2022-10-26 | 2022-10-26 | Sprint 05 | High | Improvement 🚀, Task 🔨 | Complete | October 26, 2022 23:10 | October 26, 2022 23:48 | 0 | Causes errors and the page turns completely white because the following exception occurs Rendered fewer hooks than expected. This may be caused by an accidental early return statement. Update: Initial date: 20 August 0:20 → 21 August 23:23 Now no errors | 2280 | 0 | 2280 | August 20, 2022 12:14 AM
Add end date to sessions, to not verify on each token every 15 minutes to check if it has expired. | 2022-10-28 | 2022-10-28 | Sprint 05 | Medium | Improvement 🚀, Refactor 🛠️ | Complete | October 28, 2022 1:35 | October 28, 2022 1:56 | 0 |  | 1260 | 0 | 1260 | October 22, 2022 12:15 AM
Remove refresh token from sessions, because it is not used | 2022-10-28 | 2022-10-28 | Sprint 05 | High | Refactor 🛠️ | Complete | October 28, 2022 1:57 | October 28, 2022 2:40 | 0 | Also from frontend in Redux | 2580 | 0 | 2580 | October 28, 2022 1:37 AM
Administration button to schedule the restart of the server | 2022-10-29 | 2022-10-29 | Sprint 05 | Very high | Improvement 🚀 | Complete | October 29, 2022 0:40 | October 29, 2022 16:06 | 8 |  | 55560 | 28800 | 26760 | October 27, 2022 12:56 PM
Refactor connection to web socket server by adding one previous step to joining the chat | 2022-10-30 | 2022-10-30 | Sprint 05 | High | Improvement 🚀, Refactor 🛠️, Task 🔨 | Complete | October 30, 2022 0:39 | October 30, 2022 1:18 | 0 | Now messages can be sent without being in a chat | 2340 | 0 | 2340 | October 30, 2022 12:38 AM
Add a new page to send information message to all users | 2022-10-30 | 2022-10-31 | Sprint 05 | High | Improvement 🚀 | Complete | October 30, 2022 22:30 | October 31, 2022 2:34 | 0 | In frontend we make a new page with a chat (only for administrators) and every message that is sent, is globally notified (new type and task). Also, I can define buttons to have predefined messages to send. | 14640 | 0 | 14640 | October 29, 2022 4:06 PM
Refactor commands in backend | 2022-12-10 | 2022-12-10 | Sprint 06 | Medium | Refactor 🛠️ | Complete | December 10, 2022 2:00 | December 10, 2022 3:00 | 0 | New record with several fields and removed from the CommandStrategy interface | 3600 | 0 | 3600 | December 10, 2022 3:33 AM
Send logs to Grafana with Loki | 2022-12-05 | 2022-12-07 | Sprint 06 | High | Improvement 🚀 | Complete | December 5, 2022 20:00 | December 7, 2022 1:00 | 16 | Improve by making a custom archive to send the logs to and read from that | 104400 | 57600 | 46800 | December 6, 2022 11:08 PM
Web Socket does not connect to backend in production | 2022-11-11 | 2022-11-16 | Sprint 06 | Critical 🔥 | Bug 🐞, Task 🔨 | Complete | November 11, 2022 18:30 | November 16, 2022 1:28 | -1 | Brave Browser was blocking the connection 😭 | 370680 | 0 | 370680 | November 10, 2022 10:10 PM
Refactor all the controllers. When an exception is thrown in other method, catch it to send a response message to show to the user | 2022-11-15 | 2022-11-16 | Sprint 06 | Very high | Refactor 🛠️, Task 🔨 | Complete | November 15, 2022 23:28 | November 16, 2022 19:24 | 14 | Change the error message retrieval in frontend. Can be rolled back to not using this, since the exceptions are sent if thrown in other method, but the message retrieval changes a bit. | 71760 | 50400 | 21360 | November 15, 2022 11:27 PM
Check response bodies in frontend | 2022-11-16 | 2022-11-16 | Sprint 06 | Very high | Refactor 🛠️, Task 🔨 | Complete | November 16, 2022 20:00 | November 16, 2022 20:06 | 0 |  | 360 | 0 | 360 | November 16, 2022 6:55 PM
Backend logging division by level | 2022-11-16 | 2022-11-17 | Sprint 06 | Very high | Configuration ⚙️, Improvement 🚀 | Complete | November 16, 2022 23:30 | November 17, 2022 0:05 | 0 |  | 2100 | 0 | 2100 | November 17, 2022 12:07 AM
Implement individual chats | 2022-11-17 | 2022-11-18 | Sprint 06 | Very high | Improvement 🚀 | Complete | November 17, 2022 16:35 | November 18, 2022 15:41 | 3 | Now do this → Do not refresh page when changing chat. Clear history, info and users (https://www.notion.so/Do-not-refresh-page-when-changing-chat-Clear-history-info-and-users-66031452a56f40d285fee01ed86e6170?pvs=21) | 83160 | 10800 | 72360 | November 17, 2022 2:24 PM
Change IDOR (Insecure Direct Object Reference) when showing the chat URL | 2022-11-18 | 2022-11-20 | Sprint 06 | High | Bug 🐞, Improvement 🚀, Security 🔒 | Complete | November 18, 2022 20:54 | November 20, 2022 0:22 | 8 | Check this video for explanation: https://www.youtube.com/watch?v=rloqMGcPMkI IDOR - fix with new reducer in frontend (history of all pages visited) | 98880 | 28800 | 70080 | November 18, 2022 8:28 PM
Teacher routes in frontend | 2022-11-20 |  | Sprint 06 | Medium | Improvement 🚀 | In Progress | November 20, 2022 12:37 |  |  |  |  | 0 | 0 | November 20, 2022 12:36 PM
View profile functionality. Username is used in URL | 2022-11-20 |  | Sprint 06 | Medium | Improvement 🚀 | In Progress | November 20, 2022 2:06 |  |  |  |  | 0 | 0 | November 20, 2022 2:05 AM
Improve observability with Grafana | 2022-11-27 | 2022-12-07 | Sprint 06 | Medium | Configuration ⚙️, Improvement 🚀 | Complete | November 27, 2022 0:14 | December 7, 2022 17:15 | -1 | https://grafana.com/blog/2022/04/26/set-up-and-observe-a-spring-boot-application-with-grafana-cloud-prometheus-and-opentelemetry/ Also add Loki for managing the logs | 925260 | 0 | 925260 | October 23, 2022 5:10 PM
Add new commands for fun (roll a dice, 8 ball, …) | 2022-12-10 | 2022-12-16 | Sprint 07 | Low | Improvement 🚀 | Complete | December 10, 2022 3:40 | December 16, 2022 3:00 | -1 |  | 516000 | 0 | 516000 | December 10, 2022 3:54 AM
Add support for multi-parameter commands and multiple commands in one message | 2022-12-11 | 2022-12-13 | Sprint 07 | High | Bug 🐞, Improvement 🚀 | Complete | December 11, 2022 0:00 | December 13, 2022 0:36 | 24 | Implement a parser in backend to correctly send messages. It must support multiple parameters for a command and several commands in one message | 174960 | 86400 | 88560 | December 10, 2022 4:12 AM
Send mention message to the mentioned user to notify in frontend | 2022-12-16 | 2022-12-16 | Sprint 07 | Medium | Improvement 🚀 | Complete | December 16, 2022 1:40 | December 16, 2022 20:07 | 12 |  | 66420 | 43200 | 23220 | December 16, 2022 1:40 AM
Mark html containing the mentioned user | 2022-12-16 | 2022-12-17 | Sprint 07 | Low | Improvement 🚀 | Complete | December 16, 2022 20:46 | December 17, 2022 0:13 | 1 |  | 12420 | 3600 | 8820 | December 16, 2022 8:46 PM
Know how to add custom stats to send to Prometheus | 2022-12-17 | 2022-12-17 | Sprint 07 | Medium | Configuration ⚙️, Improvement 🚀 | Complete | December 17, 2022 2:49 | December 17, 2022 3:20 | 0 | https://fabianlee.org/2022/06/29/java-adding-custom-metrics-to-spring-boot-micrometer-prometheus-endpoint/ | 1860 | 0 | 1860 | December 17, 2022 2:49 AM
When sending a non-text message, the Handler crashes because the content could not be read as normal text. | 2022-12-17 | 2022-12-17 | Sprint 07 | Very high | Bug 🐞 | Complete | December 17, 2022 20:35 | December 17, 2022 22:57 | 1 | Check the type before the content | 8520 | 3600 | 4920 | December 17, 2022 8:48 PM
Add teacher to subject by administrator | 2022-12-18 | 2022-12-21 | Sprint 07 | High | Improvement 🚀, Task 🔨 | Complete | December 18, 2022 14:52 | December 21, 2022 17:44 | 28 | 2 columns in UI: Left with teacher names and id, Right with subject names. With a search bar for each column | 269520 | 100800 | 168720 | December 18, 2022 2:51 PM
Teacher service to get data | 2022-12-18 | 2022-12-18 | Sprint 07 | High | Task 🔨 | Complete | December 18, 2022 2:08 | December 18, 2022 4:00 | 0 |  | 6720 | 0 | 6720 | December 18, 2022 2:28 AM
Fix /dice command. Page crashes | 2022-12-21 | 2022-12-21 | Sprint 07 | Very high | Bug 🐞 | Complete | December 21, 2022 0:20 | December 21, 2022 0:50 | 0 |  | 1800 | 0 | 1800 | December 20, 2022 4:59 PM
Implement rate limit to avoid spamming a lot of messages in short time | 2023-02-01 | 2023-02-01 | Sprint 08 | High | Improvement 🚀 | Complete | February 1, 2023 0:40 | February 1, 2023 15:24 | 8 | Messages that are sent after the notification of TOO_FAST_MESSAGE are deleted from the user chat view | 53040 | 28800 | 24240 | December 23, 2022 8:54 PM
Big refactor to inject some objects to message strategies | 2023-02-01 | 2023-02-01 | Sprint 08 | High | Improvement 🚀, Refactor 🛠️ | Complete | February 1, 2023 19:38 | February 1, 2023 21:06 | 0 |  | 5280 | 0 | 5280 | February 1, 2023 7:37 PM
Fix problems when sending a media message after uploading it | 2023-02-10 | 2023-02-10 | Sprint 08 | Very high | Bug 🐞 | Complete | February 10, 2023 2:00 | February 10, 2023 2:30 | 0 |  | 1800 | 0 | 1800 | February 10, 2023 2:16 AM
DTO for upload strategies | 2023-02-10 | 2023-02-10 | Sprint 08 | Low | Refactor 🛠️ | Complete | February 10, 2023 2:48 | February 10, 2023 3:01 | 0 |  | 780 | 0 | 780 | February 10, 2023 1:59 AM
Rank system, get a chat badge (or different colors) when user has written a lot of messages | 2023-02-06 | 2023-02-07 | Sprint 08 | Very low | Idea 🧠, Improvement 🚀 | Complete | February 6, 2023 0:47 | February 7, 2023 3:52 | 10 | This implies changes to the database, temporal changes made with red (in the drawings) | 97500 | 36000 | 61500 | October 10, 2022 5:16 PM
Create the design of the badges | 2023-02-07 | 2023-02-07 | Sprint 08 | Medium | Task 🔨 | Complete | February 7, 2023 11:50 | February 7, 2023 16:48 | 2 | https://badge.design/ https://pictogrammers.com/library/mdi/ https://vectorink.io/app/ | 17880 | 7200 | 10680 | February 7, 2023 11:52 AM
Badge view in profile or new page | 2023-02-07 | 2023-02-08 | Sprint 08 | Medium | Improvement 🚀 | Complete | February 7, 2023 18:30 | February 8, 2023 20:53 | 0 | Also added stats | 94980 | 0 | 94980 | February 7, 2023 6:30 PM
Fix serialization problems of JsonObject when sending responses | 2023-02-08 | 2023-02-08 | Sprint 08 | Very high | Improvement 🚀, Refactor 🛠️ | Complete | February 8, 2023 1:05 | February 8, 2023 2:50 | 0.5 | New Serializers for ObjectMapper | 6300 | 1800 | 4500 | February 8, 2023 12:21 AM
Revise the JSON.parse method calls in frontend to check if they must be removed since the JSON is sent correctly now | 2023-02-08 | 2023-02-08 | Sprint 08 | High | Task 🔨 | Complete | February 8, 2023 12:32 | February 8, 2023 17:21 | 1 |  | 17340 | 3600 | 13740 | February 8, 2023 3:50 AM
When reconnecting to a chat, the history is not retrieved | 2023-02-08 | 2023-02-08 | Sprint 08 | Very high | Bug 🐞 | Complete | February 8, 2023 19:30 | February 8, 2023 19:48 | 0 | Detected in websocket readyState | 1080 | 0 | 1080 | February 1, 2023 9:06 PM
Other users should not receive the command message if it is for own use. Mentions are sent to all users | 2023-02-09 | 2023-02-09 | Sprint 08 | Medium | Improvement 🚀 | Complete | February 9, 2023 11:55 | February 9, 2023 14:31 | 0.5 |  | 9360 | 1800 | 7560 | February 9, 2023 1:56 PM
New DTO for handling commands | 2023-02-09 | 2023-02-09 | Sprint 08 | Medium | Refactor 🛠️ | Complete | February 9, 2023 2:00 | February 9, 2023 2:15 | 0 |  | 900 | 0 | 900 | February 9, 2023 2:06 AM
Move command instantiation to its class as static members | 2023-02-09 | 2023-02-09 | Sprint 08 | Medium | Improvement 🚀, Refactor 🛠️ | Complete | February 9, 2023 21:18 | February 9, 2023 21:53 | 0 |  | 2100 | 0 | 2100 | February 9, 2023 9:18 PM
Count the commands used and save it in the user’s column in db | 2023-02-09 | 2023-02-09 | Sprint 08 | Low | Improvement 🚀 | Complete | February 9, 2023 21:54 | February 9, 2023 22:14 | 0 |  | 1200 | 0 | 1200 | February 9, 2023 9:53 PM
Add Quartz lib to schedule all the tasks. | 2023-01-15 | 2023-01-15 | Sprint 08 | Medium | Improvement 🚀 | Cancelled | January 15, 2023 13:50 | January 15, 2023 14:00 | 0 |  | 600 | 0 | 600 | January 15, 2023 3:22 AM
Refactor of if statements in Policies class to use Yavi validation library | 2023-01-20 | 2023-01-20 | Sprint 08 | Very high | Improvement 🚀, Refactor 🛠️ | Complete | January 20, 2023 12:35 | January 20, 2023 23:42 | 3 |  | 40020 | 10800 | 29220 | January 20, 2023 3:23 AM
Add teachers to degree by administrator | 2023-01-22 | 2023-01-22 | Sprint 08 | Very high | Improvement 🚀, Task 🔨 | Complete | January 22, 2023 16:19 | January 22, 2023 17:15 | 0 | Teachers are added implicitly to the degrees when they are added to a subject. Modify admin dashboard to show the degree of each subject | 3360 | 0 | 3360 | January 22, 2023 4:19 PM
Huge refactor to use JPA Buddy when generating entities and relationships | 2023-01-22 | 2023-01-24 | Sprint 08 | Critical 🔥 | Refactor 🛠️ | Complete | January 22, 2023 17:34 | January 24, 2023 21:46 | 24 | https://www.youtube.com/watch?v=DC6FrC4olhE | 187920 | 86400 | 101520 | January 22, 2023 5:33 PM
File caching to not read files from disk all times | 2023-01-25 | 2023-01-26 | Sprint 08 | Very high | Improvement 🚀 | Complete | January 25, 2023 15:54 | January 26, 2023 0:32 | 45049 |  | 31080 | 12600 | 18480 | January 25, 2023 3:53 PM
Implement pagination of the chat history | 2023-01-25 | 2023-01-26 | Sprint 08 | Medium | Improvement 🚀, Task 🔨 | Complete | January 25, 2023 15:54 | January 26, 2023 16:38 |  | Add a “Show more” button in the top of the chat | 89040 | 0 | 89040 | August 23, 2022 7:56 PM
Spring migration from 2.7.0 to 3.0.2 | 2023-01-26 | 2023-01-26 | Sprint 08 | High | Improvement 🚀, Refactor 🛠️, Security 🔒, Task 🔨 | Complete | January 26, 2023 16:45 | January 26, 2023 22:00 | 45078 |  | 18900 | 5760 | 13140 | January 25, 2023 1:52 AM
Add JWTService class and change library to jjwt | 2023-01-26 | 2023-01-27 | Sprint 08 | Low | Refactor 🛠️ | Complete | January 26, 2023 22:06 | January 27, 2023 1:58 | 45018 |  | 13920 | 8640 | 5280 | January 26, 2023 11:11 PM
Delegate functionality to Chat class instead of ChatManagement | 2023-01-30 | 2023-01-30 | Sprint 08 | High | Improvement 🚀, Refactor 🛠️ | Complete | January 30, 2023 2:10 | January 30, 2023 4:24 | 0 | Also improved code readability of both classes | 8040 | 0 | 8040 | January 30, 2023 4:24 AM
Mappings for Upload strategies | 2023-01-30 | 2023-01-30 | Sprint 08 | High | Improvement 🚀 | Complete | January 30, 2023 20:34 | January 30, 2023 21:05 | 0 | Instead of using Map, an ArrayList of new value object is used | 1860 | 0 | 1860 | January 30, 2023 11:54 PM
Bugfix: history file is deleted from disk after 10 minutes (scheduled task) but should not be deleted unless there is no users in the chat | 2023-01-30 | 2023-01-30 | Sprint 08 | Very high | Bug 🐞 | Complete | January 30, 2023 23:45 | January 30, 2023 23:53 | 0 |  | 480 | 0 | 480 | January 30, 2023 11:52 PM
Bugfix: uri is not a property in messages, it was changed to path | 2023-01-31 | 2023-01-31 | Sprint 08 | Critical 🔥 | Bug 🐞 | Complete | January 31, 2023 0:20 | January 31, 2023 0:25 | 0 |  | 300 | 0 | 300 | January 31, 2023 12:24 AM
Close all sessions does not work well (after doing it, I continued to the chat page in other tab) | 2023-01-31 | 2023-01-31 | Sprint 08 | High | Bug 🐞 | Complete | January 31, 2023 13:20 | January 31, 2023 14:10 | 0 |  | 3000 | 0 | 3000 | January 26, 2023 3:20 AM
Remove from shouldNotSomething tests the given save to the repository | 2023-02-14 | 2023-02-14 | Sprint 09 | High | Refactor 🛠️, Test 🧪 | Complete | February 14, 2023 1:31 | February 14, 2023 2:08 | 0 | Also improved existing tests and added more | 2220 | 0 | 2220 | February 14, 2023 1:29 AM
Script to update secrets in GitHub for tests | 2023-02-14 | 2023-02-14 | Sprint 09 | High | Improvement 🚀, Security 🔒, Test 🧪 | Complete | February 14, 2023 14:08 | February 14, 2023 20:04 | 4 |  | 21360 | 14400 | 6960 | February 13, 2023 3:34 AM
Controller tests with MockMvc | 2023-02-15 |  | Sprint 09 | Medium | Improvement 🚀, Test 🧪 | In Progress | February 15, 2023 0:55 |  | 13 | See description for more details |  | 46800 | -46800 | February 15, 2023 12:58 AM
New implementation for HttpServletResponse to be able to test the controllers | 2023-02-16 | 2023-02-17 | Sprint 09 | Medium | Refactor 🛠️, Test 🧪 | Complete | February 16, 2023 1:38 | February 17, 2023 20:13 | 18 |  | 153300 | 64800 | 88500 | February 16, 2023 1:37 AM | [5 empty] | https://github.com/scastd00/rs-chat-backend/pull/37
Refactor of HttpResponse, back to previous implementation. | 2023-02-18 | 2023-02-18 | Sprint 09 | Critical 🔥 | Bug 🐞, Improvement 🚀, Refactor 🛠️, Test 🧪 | Complete | February 18, 2023 17:16 | February 18, 2023 18:51 | 0.5 |  | 5700 | 1800 | 3900 | February 18, 2023 4:07 PM | [5 empty] | https://github.com/scastd00/rs-chat-backend/pull/38
Integration tests | 2023-02-20 |  | Sprint 09 | Very high | Improvement 🚀, Test 🧪 | In Progress | February 20, 2023 17:05 |  |  | https://reflectoring.io/spring-boot-test/ Disable some beans to avoid conflicts in tests |  | 0 | 0 | February 20, 2023 5:11 PM
Make the MailSender a component | 2023-02-21 | 2023-02-21 | Sprint 09 | Medium | Configuration ⚙️, Refactor 🛠️ | Cancelled | February 21, 2023 23:30 | February 21, 2023 23:50 | 0 |  | 1200 | 0 | 1200 | February 20, 2023 5:59 PM
Update policies messages | 2023-02-22 | 2023-02-22 | Sprint 09 | High | Bug 🐞 | Complete | February 22, 2023 0:23 | February 22, 2023 1:38 | 0 | message() call overrides the default message assigned to the constraint | 4500 | 0 | 4500 | February 22, 2023 1:37 AM
Fix email sender | 2023-02-23 | 2023-02-23 | Sprint 09 | Critical 🔥 | Bug 🐞 | Complete | February 23, 2023 2:00 | February 23, 2023 2:54 | 0 | Use the package spring-boot-starter-mail instead of javax.mail https://mkyong.com/spring-boot/spring-boot-how-to-send-email-via-smtp/ | 3240 | 0 | 3240 | February 23, 2023 2:39 AM
Add a ‘Copy code’ in reset password email template | 2023-02-23 | 2023-02-23 | Sprint 09 | Medium | Task 🔨 | Complete | February 23, 2023 2:54 | February 23, 2023 3:20 | 0 |  | 1560 | 0 | 1560 | February 23, 2023 2:54 AM | [5 empty] | https://github.com/scastd00/rs-chat-backend/pull/39
Single IntelliJ project with all modules inside | 2023-02-25 | 2023-02-25 | Sprint 09 | High | Configuration ⚙️ | Complete | February 25, 2023 0:29 | February 25, 2023 0:42 | 0 | Import as modules and that’s it | 780 | 0 | 780 | February 25, 2023 12:29 AM
For image detection use nsfwjs backend lib to use the IA model | 2023-02-25 | 2023-02-25 | Sprint 09 | High | Improvement 🚀 | Complete | February 25, 2023 1:40 | February 25, 2023 23:26 | 12 | https://www.npmjs.com/package/nsfwjs#node-js-app https://github.com/tensorflow/tfjs/issues/7273#issuecomment-1384413639 | 78360 | 43200 | 35160 | February 25, 2023 12:16 AM
Use magic-8-ball api for that chat command | 2023-02-25 | 2023-02-25 | Sprint 09 | Medium | Improvement 🚀, Task 🔨 | Complete | February 25, 2023 1:40 | February 25, 2023 19:48 | 10 | https://www.eightballapi.com/docs | 65280 | 36000 | 29280 | February 25, 2023 12:13 AM
Send requests from the FileController to the utility NSFW service | 2023-03-11 | 2023-03-11 | Sprint 09 | High | Improvement 🚀, Security 🔒 | Complete | March 11, 2023 2:35 | March 11, 2023 5:34 | 0 | Store the file before the request and send the path to the NSFW service, remove multer lib from the service, since it is not used. For making the requests RestTemplate is useful. | 10740 | 0 | 10740 | March 11, 2023 5:33 AM
When showing command stats in profile, the app crashes (see image) | 2023-04-10 | 2023-04-10 | Sprint 10 | Critical 🔥 | Bug 🐞 | Complete | April 10, 2023 12:35 | April 10, 2023 14:52 | 0.7 | An object (command stats) is stored inside, and the app does not support that. | 8220 | 2520 | 5700 | April 10, 2023 4:22 AM
Improve session display in frontend (show dates, and the index is the id of the session) | 2023-04-10 | 2023-04-10 | Sprint 10 | Medium | Improvement 🚀 | Complete | April 10, 2023 14:52 | April 10, 2023 17:03 | 0 |  | 7860 | 0 | 7860 | April 10, 2023 2:51 PM
Fix app crash when sending a command that is unavailable | 2023-04-10 | 2023-04-10 | Sprint 10 | Critical 🔥 | Bug 🐞 | Complete | April 10, 2023 3:08 | April 10, 2023 4:34 | 0 | Added NoOp command | 5160 | 0 | 5160 | April 10, 2023 3:07 AM
When sending a server message, the type must be a generic one. | 2023-04-05 | 2023-04-05 | Sprint 10 | High | Refactor 🛠️ | Complete | April 5, 2023 13:00 | April 5, 2023 13:12 |  | Create a constant and update all usages of the createMessage function | 720 | 0 | 720 | April 5, 2023 2:33 AM
Kick the users out of the session when they upload the last NSFW content | 2023-04-05 | 2023-04-05 | Sprint 10 | High | Improvement 🚀 | Complete | April 5, 2023 2:03 | April 5, 2023 3:29 | 0 |  | 5160 | 0 | 5160 | March 21, 2023 11:56 PM
Check run conditions when uploading several images at once when performing the request to the Python API | 2023-04-05 | 2023-04-05 | Sprint 10 | Very high | Bug 🐞 | Complete | April 5, 2023 3:43 | April 5, 2023 4:06 | 0 | When uploading 5 nsfw images, in the DB is stored only 4 (in the user nsfw_count column). https://stackoverflow.com/questions/30346882/do-synchronized-java-methods-queue-calls | 1380 | 0 | 1380 | April 5, 2023 3:08 AM
If user is blocked, do not allow to enter the app | 2023-04-05 | 2023-04-05 | Sprint 10 | High | Improvement 🚀 | Complete | April 5, 2023 4:10 | April 5, 2023 4:20 | 0 | Very easy. Added a single check in the login endpoint and a pretty format | 600 | 0 | 600 | April 5, 2023 3:05 AM
Fix not showing the images when uploading | 2023-04-06 | 2023-04-06 | Sprint 10 | Very high | Bug 🐞 | Complete | April 6, 2023 15:57 | April 6, 2023 16:20 | 0 | Resources are uploaded to the wrong folder in S3 (uppercase) and should be stored inside the lowercase ones | 1380 | 0 | 1380 | March 14, 2023 3:50 AM
Make a form to get feedback from users | 2023-04-06 | 2023-04-08 | Sprint 10 | Very high | Research ⛰️ | Complete | April 6, 2023 16:00 | April 8, 2023 16:00 | 18 |  | 172800 | 64800 | 108000 | April 6, 2023 6:57 PM
Fix pdf not showing | 2023-04-07 | 2023-04-07 | Sprint 10 | Very high | Bug 🐞 | Complete | April 7, 2023 15:25 | April 7, 2023 16:42 | 0 | CORS policy has incorrect AllowedOrigins prop | 4620 | 0 | 4620 | April 7, 2023 1:54 PM
Configure the CORS policy when checking connectivity to the bucket | 2023-04-07 | 2023-04-07 | Sprint 10 | High | Improvement 🚀 | Complete | April 7, 2023 16:42 | April 7, 2023 22:03 | 45047 |  | 19260 | 5400 | 13860 | April 7, 2023 4:54 PM
Add friends | 2023-03-11 | 2023-03-12 | Sprint 10 | Medium | Improvement 🚀 | Complete | March 11, 2023 14:00 | March 12, 2023 3:18 | 8 | Disable users from sending messages themselves, if users see their own profile, go to the profile page (both new functionality) | 47880 | 28800 | 19080 | October 20, 2022 11:19 AM
Block users | 2023-03-11 | 2023-04-05 | Sprint 10 | Medium | Improvement 🚀 | Complete | March 11, 2023 16:00 | April 5, 2023 13:00 | -1 |  | 2145600 | 0 | 2145600 | October 20, 2022 11:31 AM
Dockerize rs-chat-utils services | 2023-03-11 | 2023-03-14 | Sprint 10 | Very high | Configuration ⚙️, Improvement 🚀 | Complete | March 11, 2023 17:45 | March 14, 2023 3:14 | 36 | https://github.com/tensorflow/tfjs/issues/1425#issuecomment-596197404 I have to build tensorflow from source or downgrade to 1.5. After compiling from source (6.7 h) found version https://github.com/yaroslavvb/tensorflow-community-wheels/issues/217 | 206940 | 129600 | 77340 | March 11, 2023 6:51 PM
Migrate nsfw service to Python | 2023-03-12 | 2023-03-14 | Sprint 10 | Critical 🔥 | Bug 🐞, Refactor 🛠️ | Complete | March 12, 2023 13:57 | March 14, 2023 2:49 | 24 | https://pythonspeed.com/articles/activate-virtualenv-dockerfile/ https://stackoverflow.com/questions/30215830/dockerfile-copy-keep-subdirectory-structure Needed to set the Internet Address to 0.0.0.0 to be able to receive external requests | 132720 | 86400 | 46320 | March 12, 2023 1:56 PM
Set to users the block date when several NSFW content is uploaded to chats | 2023-03-21 | 2023-03-21 | Sprint 10 | High | Improvement 🚀 | Complete | March 21, 2023 23:00 | March 21, 2023 23:56 | 0 |  | 3360 | 0 | 3360 | March 21, 2023 11:16 PM
Prepare environment to perform frontend tests | 2023-03-30 | 2023-03-30 | Sprint 10 | High | Configuration ⚙️, Test 🧪 | Complete | March 30, 2023 1:00 | March 30, 2023 1:10 | 0 | Simple jest execution | 600 | 0 | 600 | March 29, 2023 8:45 PM
Add more CI steps for testing | 2023-03-30 | 2023-03-30 | Sprint 10 | Medium | CI/CD 🏛️, Improvement 🚀, Test 🧪 | Complete | March 30, 2023 13:56 | March 30, 2023 15:15 | 0.5 |  | 4740 | 1800 | 2940 | March 30, 2023 1:54 PM
When users upload several NSFW images, block them for a period of time |  |  | Sprint 10 | Medium | Improvement 🚀, Task 🔨 | Reference |  |  | 0 | Set to users the block date when several NSFW content is uploaded to chats (https://www.notion.so/Set-to-users-the-block-date-when-several-NSFW-content-is-uploaded-to-chats-9d9e4a73829d4a089ee2fcdfec9bea21?pvs=21) |  | 0 | 0 | March 14, 2023 2:50 AM
Fix bug not sending email on invitation | 2023-05-01 | 2023-05-01 | Sprint 11 | High | Bug 🐞 | Complete | 2023-05-01 01:40 | 2023-05-01 01:57 | 0 | Instead of using the email, it was used the username of the invetee. Used Tuple to return the chat and the user from the lambda. | 1020 | 0 | 1020 | May 1, 2023 1:56 AM
Remove the /invite command | 2023-05-01 | 2023-05-02 | Sprint 11 | Medium | Refactor 🛠️ | Complete | 2023-05-01 13:20 | 2023-05-02 13:40 | 0 | Added the invite button in chat view | 87600 | 0 | 87600 | May 1, 2023 1:22 PM
Use Optional<T> in all return types from the repository | 2023-05-03 | 2023-05-03 | Sprint 11 | High | Refactor 🛠️ | Complete | 2023-05-03 12:39 | 2023-05-03 12:44 | 0 |  | 300 | 0 | 300 | April 9, 2023 6:41 PM
Refactor exception handling in controllers with @ControllerAdvice | 2023-05-07 |  | Sprint 11 | Medium | Refactor 🛠️ | In Progress | 2023-05-07 02:31 |  |  | https://reflectoring.io/spring-boot-exception-handling/ |  | 0 | 0 | April 9, 2023 4:12 PM
When inviting someone to a chat, send an email to the user to notify the invitation. The user is added to the chat immediately | 2023-04-11 | 2023-04-12 | Sprint 11 | Medium | Improvement 🚀 | Complete | April 11, 2023 2:05 | April 12, 2023 3:30 | 12 | Instead of a command, do a button near chat name and send a POST request. This allows to ease the process of DI and send the email to the user. | 91500 | 43200 | 48300 | April 11, 2023 2:08 AM
Refactor Utils class to not be named like that | 2023-04-30 | 2023-04-30 | Sprint 11 | Low | Documentation 📘, Refactor 🛠️ | Complete | April 30, 2023 3:25 | April 30, 2023 3:58 | 0 |  | 1980 | 0 | 1980 | April 30, 2023 3:18 AM
Fix error in profile view |  |  | Sprint 11 | Medium | Bug 🐞 | Revision | [5 empty] | 0 | 0 | April 17, 2023 2:47 AM
Add Report page for admins and display all the report notifications |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | May 8, 2023 12:42 PM
Video handling with lib |  |  |  | UNSET | Idea 🧠 | Not Started |  |  |  | https://github.com/kokorin/Jaffree https://github.com/Manevolent/ffmpeg4j |  | 0 | 0 | April 23, 2023 5:11 PM
Fix Redux localstorage modification by checking the username of the token in the backend. |  |  |  | Very high | Bug 🐞 | Not Started |  |  |  | Also the storage should be changed to other with more security |  | 0 | 0 | April 19, 2023 11:56 PM
New design when sending nsfw media |  |  |  | Medium | Improvement 🚀 | Not Started |  |  |  | The user can see the image, but other users cannot |  | 0 | 0 | April 10, 2023 6:37 PM
Send the session ip in the login and register response to identify the session in the profile view |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | April 10, 2023 4:23 PM
Do not store empty commands |  |  |  | Medium | Bug 🐞 | Not Started | [5 empty] | 0 | 0 | April 10, 2023 12:42 PM
Improve command parsing |  |  |  | Medium | Improvement 🚀, Refactor 🛠️ | Not Started | [5 empty] | 0 | 0 | April 10, 2023 2:50 AM
Improve blocked users and friends functionality and relationships in db |  |  |  | Low | Refactor 🛠️ | Not Started | [5 empty] | 0 | 0 | April 10, 2023 2:40 AM
Chats with limited number of members |  |  |  | To define | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | April 9, 2023 7:06 PM
Create group by every user (private or public) |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | April 9, 2023 2:40 PM
Unread messages balloon notification |  |  |  | Medium | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | April 9, 2023 2:31 PM
Multiple chat tabs |  |  |  | Medium | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | April 9, 2023 2:30 PM
Webcam integration |  |  |  | To define | Idea 🧠, Improvement 🚀 | Not Started |  |  |  | https://primefaces.github.io/primefaces/jsdocs/modules/src_PrimeFaces.Webcam.html |  | 0 | 0 | April 8, 2023 2:05 AM
Age verification |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | March 23, 2023 5:36 PM
Improve friends functionality to not add symmetric rows to DB |  |  |  | Medium | Improvement 🚀, Refactor 🛠️ | Not Started |  |  |  | To represent friends, with only one relation suffices (or look for other techniques). |  | 0 | 0 | March 12, 2023 3:19 AM
Report user form and send a notification to administrators of a new report. |  |  |  | Medium | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | March 12, 2023 2:12 AM
When the chat passes 1 month, delete the history |  |  |  | Medium | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | February 28, 2023 5:48 PM
Integrate the Keras NSFW model to Java (new service or integrated in the app) |  | 2023-03-11 |  | Low | Idea 🧠, Improvement 🚀 | Cancelled |  | March 11, 2023 2:30 |  | https://towardsdatascience.com/deploying-keras-deep-learning-models-with-java-62d80464f34a |  | 0 | 0 | February 27, 2023 1:50 AM
Use WebTau for E2E tests (for test the API) |  | 2023-02-21 |  | High | Improvement 🚀, Test 🧪 | Cancelled |  | February 21, 2023 23:30 |  | https://github.com/testingisdocumenting/webtau |  | 0 | 0 | February 14, 2023 3:41 AM
Make all strategies a @Component, to be able to inject attributes |  |  |  | Low | Improvement 🚀, Refactor 🛠️ | Cancelled |  |  |  | See Big refactor to inject some objects to message strategies (https://www.notion.so/Big-refactor-to-inject-some-objects-to-message-strategies-e55b16e03ffe42268749f0f0252555ee?pvs=21). Strategies do not have the annotation but all the needed arguments are passed to the constructor of the strategy from the Mappings class (this is a @Component class) |  | 0 | 0 | February 1, 2023 1:59 AM
Replace single MIME type for files with the full MIME type name |  | 2023-01-31 |  | Medium | Refactor 🛠️ | Cancelled |  | January 31, 2023 23:30 | -1 | This change would affect the storage of the files in S3 bucket |  | 0 | 0 | January 30, 2023 10:40 PM
Image recognition with deeplearning4j library |  | 2023-02-25 |  | Medium | Improvement 🚀 | Cancelled |  | February 25, 2023 0:13 |  | https://medium.com/datactw/image-classification-neural-network-tutorial-getting-started-with-deep-learning-for-java-dl4j-b36372aad656 https://www.baeldung.com/java-cnn-deeplearning4j |  | 0 | 0 | January 30, 2023 4:45 PM
Possibility to add a proxy between the client and the server |  |  |  | UNSET | Idea 🧠, Improvement 🚀, Security 🔒 | Not Started | [5 empty] | 0 | 0 | January 28, 2023 10:52 PM
Go down button with small number icon to specify the received messages |  |  |  | Medium | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | January 26, 2023 4:25 PM
10k lines of code 🎊 |  | 2023-01-26 |  | Critical 🔥 |  | Complete |  | January 26, 2023 3:35 |  |  |  | 0 | 0 | January 26, 2023 3:34 AM
Administration button to close/open chats and send to home the connected users |  | 2023-01-31 |  | Low | Improvement 🚀 | Cancelled |  | January 31, 2023 23:06 |  |  |  | 0 | 0 | January 25, 2023 5:44 PM
Special rooms for games |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started |  |  |  | TicTacToe, Bingo… |  | 0 | 0 | January 22, 2023 3:27 PM
Improve the security of my home Wi-Fi and network |  |  |  | High | Research ⛰️, Security 🔒 | Not Started | [5 empty] | 0 | 0 | December 23, 2022 10:42 PM
Add relations to entities to reduce queries |  |  |  | Low | Refactor 🛠️ | Reference |  |  |  | See Huge refactor to use JPA Buddy when generating entities and relationships (https://www.notion.so/Huge-refactor-to-use-JPA-Buddy-when-generating-entities-and-relationships-20d0e8a92bd946b8a0bd9d0f9f4dae9c?pvs=21) |  | 0 | 0 | December 23, 2022 8:48 PM
Make a table to display command help in frontend |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | December 10, 2022 3:34 AM
Fix Force Browsing the images in S3 bucket |  |  |  | Very high | Bug 🐞, Improvement 🚀, Security 🔒 | Not Started |  |  |  | See Change IDOR (Insecure Direct Object Reference) when showing the chat URL (https://www.notion.so/Change-IDOR-Insecure-Direct-Object-Reference-when-showing-the-chat-URL-9c79060be308413eaa5c4347804886d5?pvs=21) |  | 0 | 0 | November 20, 2022 12:15 PM
When user has friends and they are connected to the same chat, the first active users shown must be that friends |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | November 20, 2022 2:27 AM
Improve going back and forward with mouse buttons |  |  |  | Medium | Improvement 🚀 | Not Started |  |  |  | Store the location where the user joined the page and if there are no more entries to go back, go to that location. |  | 0 | 0 | November 20, 2022 12:24 AM
Do not refresh page when changing chat. Clear history, info and users |  | 2022-11-20 |  | High | Improvement 🚀, Task 🔨 | Cancelled |  | November 20, 2022 0:20 |  |  |  | 0 | 0 | November 18, 2022 8:52 PM
Application statistics. Maybe other application using SQS locally? |  |  |  | Medium | Improvement 🚀 | Reference |  |  |  | Ref: Chat statistics - Per user, number of messages, words written… (https://www.notion.so/Chat-statistics-Per-user-number-of-messages-words-written-e4f38babbf804ac59c7bfe6c5d4ef170?pvs=21) |  | 0 | 0 | November 6, 2022 12:36 AM
Reconnect button in ToolBar |  |  |  | Medium | Improvement 🚀 | Not Started |  |  |  | Might not be needed |  | 0 | 0 | November 2, 2022 5:11 PM
An ‘ActiveUsers’ message is sent after the client closes a chat |  |  |  | High | Bug 🐞 | Ignore |  |  |  | It is a message to get all the active users when one leaves the chat. No problem |  | 0 | 0 | November 2, 2022 4:59 PM
Migrate useEffect with API calls with useQuery |  |  |  | Medium | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | October 26, 2022 9:37 PM
Send information message when the deployment is going to be done |  |  |  | High | Configuration ⚙️, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | October 21, 2022 5:22 PM
Add to the name of the subjects and groups a random String at the end to support repeated names, but not show it when retrieving information |  |  |  | Medium | Task 🔨 | Not Started | [5 empty] | 0 | 0 | October 21, 2022 2:18 PM
Block users for 10 minutes when they introduce a wrong password |  |  |  | Medium | Improvement 🚀, Task 🔨 | Not Started |  |  |  | See description for more details |  | 0 | 0 | October 20, 2022 5:59 PM
Poll system integrated in the chat |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | October 20, 2022 12:16 AM
Create email server at home |  |  |  | High | Configuration ⚙️, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | October 18, 2022 4:07 PM
Make dockerfiles to have a dev and prod containers of the backend |  |  |  | Very high | Configuration ⚙️, Improvement 🚀 | Cancelled |  |  |  | Unnecessary. Background processes can be used |  | 0 | 0 | October 15, 2022 11:16 PM
Fix general crashes of the app |  |  |  | Critical 🔥 | Bug 🐞 | TempCancel | [5 empty] | 0 | 0 | October 12, 2022 1:08 AM
Active users table have repeated usernames (users from mobile) |  |  |  | High | Bug 🐞 | TempCancel | [5 empty] | 0 | 0 | October 12, 2022 1:07 AM
Sound must be played on every message (fix hook to execute completely and not pause the sound) |  |  |  | Low | Bug 🐞 | TempCancel | [5 empty] | 0 | 0 | October 12, 2022 1:06 AM
When mobiles quit browser when they are inside the chat, the WS crashes |  |  |  | Very high | Bug 🐞 | Not Started |  |  |  | Server must be restarted to enable users to use the chat again |  | 0 | 0 | October 12, 2022 1:02 AM
When a user wants to add another to a group, show all the available groups to that person to select one, to copy the invitation code with instructions or send an email |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | October 12, 2022 12:14 AM
Implementación de algo de funcionalidad más especial. Papers |  |  |  | Very low | Idea 🧠 | Not Started | [5 empty] | 0 | 0 | October 10, 2022 5:33 PM
FIX: max width in image dialog is not correct. See the image sent by amigueldiez |  |  |  | Medium | Bug 🐞 | Not Started | [5 empty] | 0 | 0 | September 28, 2022 11:41 PM
Add chat tabs to have several opened at the same time |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | September 28, 2022 12:57 PM
Add response messages by pressing a button or making double click |  |  |  | Medium | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | September 27, 2022 3:41 PM
FIX: when a user receives a message and the image is opened, the dialog is closed for some reason |  |  |  | Medium | Bug 🐞 | Not Started | [5 empty] | 0 | 0 | September 27, 2022 3:38 PM
Check the indexes in the LaTeX document to correctly generate the numbers |  |  |  | High | Documentation 📘 | Cancelled | [5 empty] | 0 | 0 | September 25, 2022 1:41 AM
Apply observer pattern when users join a chat |  |  |  | Medium | Improvement 🚀 | Not Started |  |  |  | Watch video |  | 0 | 0 | September 23, 2022 4:25 PM
Get all the users that belong to a chat and put a small green icon to those connected (show first), those unconnected with a red icon and last |  |  |  | Very low | Idea 🧠, Improvement 🚀, Task 🔨 | Not Started | [5 empty] | 0 | 0 | September 14, 2022 10:06 PM
Remove checks on register. Only show error when server sends the response |  |  |  | High | Refactor 🛠️, Task 🔨 | Cancelled | [5 empty] | 0 | 0 | September 11, 2022 2:04 PM
GET request to a URL with an invitation code as a parameter. Then, the user can join the chat if user is not joined and redirected to it in both cases (joined or not) |  |  |  | Very low | Idea 🧠, Task 🔨 | TempCancel | [5 empty] | 0 | 0 | September 9, 2022 4:18 AM
Group multiple images/videos in one message |  |  |  | Low | Improvement 🚀, Task 🔨 | Not Started |  |  |  | New message type constant and component |  | 0 | 0 | August 28, 2022 1:05 PM
Zoom on scroll (in images) |  |  |  | Medium | Improvement 🚀, Research ⛰️ | Not Started | [5 empty] | 0 | 0 | August 28, 2022 1:29 AM
Add a small dropdown to select the type of file the user is going to send |  |  |  | High | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | August 26, 2022 11:27 PM
Chat statistics - Per user, number of messages, words written… |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | August 26, 2022 1:48 AM
Replace disk reads for memory reads when reading chat history |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | August 23, 2022 9:20 PM
Solve problems of websocket connections in remote |  |  |  | Critical 🔥 | Bug 🐞 | Cancelled |  |  |  | There are no problems now (next day). Because the chat was closed and the history file was uploaded, so no errors occur |  | 0 | 0 | August 23, 2022 1:10 AM
Discover the limit to send data through WS to frontend |  | 2022-09-05 |  | High | Refactor 🛠️ | Cancelled |  | September 5, 2022 0:29 |  |  |  | 0 | 0 | August 23, 2022 12:52 AM
Check this lib to support message compression in frontend. Must be implemented in backend since it is written in Java |  |  |  | Very low | Idea 🧠, Improvement 🚀, Refactor 🛠️ | TempCancel | [5 empty] | 0 | 0 | August 23, 2022 12:48 AM
See this to send partial data (maybe) |  |  |  | Very low | Idea 🧠, Improvement 🚀, Refactor 🛠️ | TempCancel |  |  |  | Maybe change by https://www.notion.so/Implement-pagination-of-the-chat-history-60761d135d7c458094f1923f1b592ab8?pvs=21 |  | 0 | 0 | August 23, 2022 12:43 AM
Add a reducer for chat and store the current chat |  |  |  | Medium | Improvement 🚀 | TempCancel |  |  |  | Update it before going to the page and take it from the state to show its name in the chat view |  | 0 | 0 | August 23, 2022 12:37 AM
Add a global variable in redux state and a custom hook to get the websocket client only when the variable is true (userLoggedIn), if false, create client and then return. This will work like the color theme. |  |  |  | Medium | Improvement 🚀, Refactor 🛠️ | Cancelled |  |  |  | It is implemented with a React Context |  | 0 | 0 | August 17, 2022 12:32 PM
Remove sessionId of the user both in frontend and backend |  |  |  | Medium | Refactor 🛠️ | Revision |  |  |  | Could be kept to support multi-session connections |  | 0 | 0 | August 16, 2022 4:39 PM
Try the reconnection of the WebSocket in frontend |  |  |  | Medium | Improvement 🚀 | Complete |  |  |  | Reference Send a ping message from frontend to keep the connection alive (https://www.notion.so/Send-a-ping-message-from-frontend-to-keep-the-connection-alive-8d8a3f5705f642b5be84dd33351c6036?pvs=21) |  | 0 | 0 | August 15, 2022 4:57 PM
If several messages are received from the same sender, do not render the username |  |  |  | Very low | Idea 🧠, Task 🔨 | Not Started | [5 empty] | 0 | 0 | August 12, 2022 3:46 PM
Add support to compute the color hash that a user has. |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | August 9, 2022 11:50 PM
Classes diagram |  |  |  | High | Documentation 📘 | Not Started | [5 empty] | 0 | 0 | August 9, 2022 9:52 PM
Interaction diagram |  |  |  | High | Documentation 📘 | Not Started | [5 empty] | 0 | 0 | August 9, 2022 9:52 PM
Packages diagram |  |  |  | High | Documentation 📘 | Not Started | [5 empty] | 0 | 0 | August 9, 2022 9:52 PM
Send a confirmation email to new registered users |  |  |  | Medium | Security 🔒, Task 🔨 | Not Started | [5 empty] | 0 | 0 | August 9, 2022 5:56 PM
Add the service files to the frontend |  |  |  | Medium | Task 🔨 | Ignore | [5 empty] | 0 | 0 | August 6, 2022 2:26 PM
Move ChatMap functionality to Chat class |  |  |  | Low | Refactor 🛠️, Task 🔨 | Not Started | [5 empty] | 0 | 0 | August 5, 2022 8:40 PM
Use a context in private routes to encapsulate a single WebSocket for all the session |  | 2022-08-04 |  | High | Improvement 🚀, Task 🔨 | Cancelled |  | August 4, 2022 22:30 |  |  |  | 0 | 0 | August 3, 2022 6:49 PM
Upload images from frontend with drag ’n’ drop and encode into base64 |  |  |  | High | Task 🔨 | Reference | [5 empty] | 0 | 0 | August 3, 2022 12:20 AM
Add random generated string at the end of media files |  |  |  | Medium | Improvement 🚀, Task 🔨 | Not Started | [5 empty] | 0 | 0 | August 1, 2022 11:54 PM
Get all files that a user has sent over the time |  |  |  | Very low | Idea 🧠 | Not Started | [5 empty] | 0 | 0 | August 1, 2022 11:01 PM
Achievements’ system |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | August 1, 2022 4:14 PM
Migrate from native WebSocket to SockJS and |  | 2022-07-30 |  | Medium | Refactor 🛠️ | Cancelled |  | July 30, 2022 23:00 |  | See https://www.notion.so/Migrate-from-Java-WebSocket-lib-to-Jetty-websockets-in-backend-2741493312a847c8a769338bb49b9b63?pvs=21. Tested but it did not work. |  | 0 | 0 | July 29, 2022 1:10 AM
If up arrow key is pressed, visit the message history |  |  |  | Very low | Idea 🧠, Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | July 27, 2022 10:27 PM
Limit rate at which users can send messages to 6 per second |  |  |  | Very low | Idea 🧠, Improvement 🚀, Task 🔨 | Not Started | [5 empty] | 0 | 0 | July 26, 2022 6:08 PM
Return an existing session to the user that logs in with other host |  |  |  | Very low | Idea 🧠, Improvement 🚀, Task 🔨 | Not Started | [5 empty] | 0 | 0 | July 26, 2022 6:05 PM
Logout check |  |  |  | Low |  | Not Started | [5 empty] | 0 | 0 | July 25, 2022 10:32 AM
Messages could be fragmented. Add an attribute in the JSON |  |  |  | Very low | Idea 🧠 | Cancelled | [5 empty] | 0 | 0 | July 25, 2022 3:18 AM
File writing from several threads (maybe use synchronized) |  |  |  | Low |  | Cancelled | [5 empty] | 0 | 0 | July 24, 2022 1:29 AM
When hovering the date of the message, show full date (with millisecond precision) |  |  |  | Low | Task 🔨 | Reference | [5 empty] | 0 | 0 | July 21, 2022 12:05 AM
Show a division of messages per day |  |  |  | Low | Task 🔨 | Not Started | [5 empty] | 0 | 0 | July 21, 2022 12:05 AM
Font size selector |  |  |  | Low | Improvement 🚀, Task 🔨 | Not Started | [5 empty] | 0 | 0 | July 21, 2022 12:04 AM
Enter the app as anonymous user and after the session is closed, all the data, messages, etc. is deleted |  |  |  | Very low | Idea 🧠 | Cancelled | [5 empty] | 0 | 0 | July 5, 2022 9:55 AM
Change color themes to fit logo |  |  |  | Low | Improvement 🚀 | Not Started | [5 empty] | 0 | 0 | June 26, 2022 12:02 AM
Home page with chat selection |  |  |  | Medium | Task 🔨 | Reference | [5 empty] | 0 | 0 | June 25, 2022 11:49 PM
Forgot password functionality |  |  |  | Medium | Task 🔨 | Reference | [5 empty] | 0 | 0 | June 20, 2022 8:25 PM
Documentation - All diagrams |  |  |  | High | Documentation 📘, Initialization 🎉 | Not Started | [5 empty] | 0 | 0 | June 17, 2022 3:55 PM
Ability to close all sessions of the user |  |  |  | Medium | Task 🔨 | Not Started | [5 empty] | 0 | 0 | June 14, 2022 9:58 PM
SessionService update when refreshToken is used |  |  |  | Medium | Task 🔨 | Not Started | [5 empty] | 0 | 0 | June 14, 2022 9:36 PM
Document - Use cases |  |  |  | High | Documentation 📘, Initialization 🎉 | Not Started | [5 empty] | 0 | 0 | June 14, 2022 2:56 AM
Probar el módulo de traducción en Frontend |  |  |  | Very low | Idea 🧠 | Not Started | [5 empty] | 0 | 0 | June 12, 2022 1:52 AM
Sistema de menciones |  |  |  | Very low | Idea 🧠, Research ⛰️ | Not Started | [5 empty] | 0 | 0 | June 10, 2022 4:41 AM
How To Build React with Java Backend For Production ¦ by Bhargav Bachina ¦ Bachina Labs ¦ Medium |  |  |  | Very low | Idea 🧠, Research ⛰️ | Complete | [5 empty] | 0 | 0 | June 10, 2022 3:14 AM | [5 empty] | https://medium.com/bb-tutorials-and-thoughts/how-to-build-react-with-java-backend-for-production-72f8634bb067
How To Develop and Build React App With Java Backend ¦ by Bhargav Bachina ¦ Bachina Labs ¦ Medium |  |  |  | Very low | Idea 🧠, Research ⛰️ | Complete | [5 empty] | 0 | 0 | June 10, 2022 3:13 AM | [5 empty] | https://medium.com/bb-tutorials-and-thoughts/how-to-develop-and-build-react-app-with-java-backend-c1e6c5c93ae